## >> HOME <<
PORTFOLIO MANAGEMENT SYSTEM v4.0
>> DASHBOARD << | View Executive Report
>> DEMAND_PLAN << | Future Resource Needs
>> RES_HEATMAP << | Current Capacity
DB_Projects | Manage Projects
DB_Allocations | Assign Resources
DB_Milestones | Track Milestones
DB_Financials | Budget vs Actuals
DB_Resources | Resource Master
DB_Pipeline | Future Opportunities

## >> DASHBOARD <<
EXECUTIVE SUMMARY
Total Projects: | 25
Total Budget: | 7070000
Budget Utilized: | 33.36%
Project | Portfolio | Team | Goal | Status | Budget_Status | Roadmap | Resources | Narrative
Project J-09 | Cloud Infra | Core Ops | Q4-2032 | Red | Amber | ✅ Discovery (100%) 🔵 Build (40%) | • Tom (Python/AI) • Wei (Java Fullstack) | GOAL: Finalize UAT RISK: Staffing
Project L-11 | Cloud Infra | Core Ops | Q4-2026 | Amber | Amber | ✅ Discovery (100%) ⚠️ Build (40%) | • John (SAP ABAP) • Sarah (Data Engineering) • Tom (Python/AI) | GOAL: Finalize UAT RISK: Staffing
Project U-20 | Cloud Infra | Core Ops | Q1-2030 | Green | Green | ✅ Discovery (100%) ⚠️ Build (40%) | • John (SAP ABAP) • Ravi (Java Fullstack) | GOAL: Finalize UAT RISK: None
Project W-22 | Cloud Infra | Squad Alpha | Q3-2030 | Amber | Green | ✅ Discovery (100%) ⚠️ Build (40%) | • Jessica (Python/AI) • Wei (Java Fullstack) • John (SAP ABAP) | GOAL: Finalize UAT RISK: Staffing
Project B-01 | Cloud Infra | Squad Beta | Q2-2027 | Red | Amber | ✅ Discovery (100%) 🔵 Build (40%) | • John (SAP ABAP) • Mike (Java Fullstack) • Wei (Java Fullstack) | GOAL: Finalize UAT RISK: Staffing
Project G-06 | Cloud Infra | Squad Beta | Q3-2027 | Amber | Green | ✅ Discovery (100%) 🔵 Build (40%) | • John (SAP ABAP) • Lisa (Data Engineering) | GOAL: Finalize UAT RISK: Staffing
Project Y-24 | Cloud Infra | Squad Beta | Q3-2029 | Red | Green | ✅ Discovery (100%) 🔵 Build (40%) | • Tom (Python/AI) • Lisa (Data Engineering) • Sarah (Data Engineering) | GOAL: Finalize UAT RISK: Staffing
Project D-03 | Data & AI | Core Ops | Q2-2027 | Green | Green | ✅ Discovery (100%) 🔵 Build (40%) | • Ravi (Java Fullstack) • Lisa (Data Engineering) • Tom (Python/AI) | GOAL: Finalize UAT RISK: None
Project Q-16 | Data & AI | Core Ops | Q3-2027 | Amber | Amber | ✅ Discovery (100%) 🔵 Build (40%) | • Tom (Python/AI) • Sarah (Data Engineering) • John (SAP ABAP) | GOAL: Finalize UAT RISK: Staffing
Project N-13 | Data & AI | Squad Alpha | Q4-2030 | Amber | Green | ✅ Discovery (100%) ⚠️ Build (40%) | • Mike (Java Fullstack) • Ravi (Java Fullstack) | GOAL: Finalize UAT RISK: Staffing
Project R-17 | Data & AI | Squad Beta | Q2-2027 | Red | Amber | ✅ Discovery (100%) ⚠️ Build (40%) | • Sarah (Data Engineering) • Lisa (Data Engineering) | GOAL: Finalize UAT RISK: Staffing
Project Z-25 | Data & AI | Squad Gamma | Q2-2031 | Amber | Green | ✅ Discovery (100%) 🔵 Build (40%) | • Jessica (Python/AI) • Tom (Python/AI) | GOAL: Finalize UAT RISK: Staffing
Project C-02 | Digital Transformation | Core Ops | Q4-2031 | Amber | Green | ✅ Discovery (100%) 🔵 Build (40%) | • Priya (Python/AI) • Mike (Java Fullstack) • Lisa (Data Engineering) | GOAL: Finalize UAT RISK: Staffing
Project T-19 | Digital Transformation | Core Ops | Q1-2029 | Amber | Green | ✅ Discovery (100%) 🔵 Build (40%) | • John (SAP ABAP) • Sarah (Data Engineering) • Wei (Java Fullstack) | GOAL: Finalize UAT RISK: Staffing
Project I-08 | Digital Transformation | Squad Alpha | Q3-2033 | Amber | Green | ✅ Discovery (100%) ⚠️ Build (40%) | • Sarah (Data Engineering) • Siva (Java Fullstack) | GOAL: Finalize UAT RISK: Staffing
Project O-14 | Digital Transformation | Squad Alpha | Q4-2026 | Amber | Green | ✅ Discovery (100%) ⚠️ Build (40%) | • Siva (Java Fullstack) • Lisa (Data Engineering) • Sarah (Data Engineering) | GOAL: Finalize UAT RISK: Staffing
Project M-12 | Digital Transformation | Squad Beta | Q3-2032 | Red | Green | ✅ Discovery (100%) 🔵 Build (40%) | • John (SAP ABAP) • Priya (Python/AI) | GOAL: Finalize UAT RISK: Staffing
Project S-18 | Digital Transformation | Squad Beta | Q1-2030 | Green | Green | ✅ Discovery (100%) ⚠️ Build (40%) | • Ravi (Java Fullstack) • Priya (Python/AI) | GOAL: Finalize UAT RISK: None
Project H-07 | Digital Transformation | Squad Gamma | Q4-2029 | Amber | Green | ✅ Discovery (100%) 🔵 Build (40%) | • Lisa (Data Engineering) • Wei (Java Fullstack) • Sarah (Data Engineering) | GOAL: Finalize UAT RISK: Staffing
Project E-04 | Legacy Modernization | Core Ops | Q3-2032 | Amber | Amber | ✅ Discovery (100%) ⚠️ Build (40%) | • Wei (Java Fullstack) • Ravi (Java Fullstack) | GOAL: Finalize UAT RISK: Staffing
Project K-10 | Legacy Modernization | Core Ops | Q2-2031 | Red | Amber | ✅ Discovery (100%) ⚠️ Build (40%) | • Mike (Java Fullstack) • Jessica (Python/AI) • Sarah (Data Engineering) | GOAL: Finalize UAT RISK: Staffing
Project P-15 | Legacy Modernization | Squad Alpha | Q3-2029 | Green | Green | ✅ Discovery (100%) 🔵 Build (40%) | • Priya (Python/AI) • John (SAP ABAP) | GOAL: Finalize UAT RISK: None
Project X-23 | Legacy Modernization | Squad Beta | Q4-2027 | Amber | Amber | ✅ Discovery (100%) 🔵 Build (40%) | • Sarah (Data Engineering) • Jessica (Python/AI) • Wei (Java Fullstack) | GOAL: Finalize UAT RISK: Staffing
Project F-05 | Legacy Modernization | Squad Gamma | Q3-2027 | Green | Green | ✅ Discovery (100%) 🔵 Build (40%) | • Sarah (Data Engineering) • John (SAP ABAP) • Siva (Java Fullstack) | GOAL: Finalize UAT RISK: None
Project V-21 | Legacy Modernization | Squad Gamma | Q2-2029 | Amber | Green | ✅ Discovery (100%) 🔵 Build (40%) | • John (SAP ABAP) • Ravi (Java Fullstack) • Lisa (Data Engineering) | GOAL: Finalize UAT RISK: Staffing

## >> DEMAND_PLAN <<
Portfolio | Team | Goal | Skill Required | Level | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01
Data & AI | Squad Alpha | Q1-2026 | Data Engineering | Senior | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legacy Modernization | Squad Alpha | Q4-2030 | Cloud/DevOps | Senior | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legacy Modernization | Squad Beta | Q2-2029 | Cloud/DevOps | Standard | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legacy Modernization | Core Ops | Q3-2032 | Cloud/DevOps | Senior | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cloud Infra | Squad Alpha | Q3-2030 | SAP ABAP | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Cloud Infra | Squad Beta | Q2-2030 | Python/AI | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Cloud Infra | Core Ops | Q3-2033 | Java Fullstack | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Legacy Modernization | Squad Alpha | Q1-2029 | Java Fullstack | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
Legacy Modernization | Core Ops | Q1-2027 | Java Fullstack | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
Legacy Modernization | Squad Beta | Q2-2032 | SAP ABAP | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Digital Transformation | Squad Alpha | Q4-2031 | SAP ABAP | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Digital Transformation | Squad Alpha | Q3-2026 | Python/AI | Senior | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Digital Transformation | Squad Gamma | Q3-2030 | Cloud/DevOps | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Digital Transformation | Core Ops | Q1-2029 | Java Fullstack | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Legacy Modernization | Squad Alpha | Q2-2028 | Python/AI | Standard | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cloud Infra | Squad Alpha | Q2-2027 | Java Fullstack | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
Data & AI | Core Ops | Q1-2032 | Python/AI | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
Cloud Infra | Squad Gamma | Q2-2028 | Data Engineering | Standard | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cloud Infra | Squad Alpha | Q4-2033 | Data Engineering | Standard | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cloud Infra | Squad Gamma | Q1-2030 | Data Engineering | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
Legacy Modernization | Squad Gamma | Q2-2033 | Data Engineering | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Legacy Modernization | Squad Beta | Q3-2029 | SAP ABAP | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legacy Modernization | Squad Beta | Q3-2027 | Java Fullstack | Senior | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Digital Transformation | Squad Beta | Q1-2032 | Java Fullstack | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Digital Transformation | Squad Gamma | Q2-2029 | SAP ABAP | Standard | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legacy Modernization | Core Ops | Q4-2029 | Data Engineering | Standard | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Digital Transformation | Core Ops | Q2-2032 | Python/AI | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legacy Modernization | Squad Alpha | Q1-2027 | Data Engineering | Senior | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data & AI | Squad Alpha | Q4-2031 | Python/AI | Senior | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Digital Transformation | Squad Beta | Q4-2026 | Data Engineering | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1

## >> RES_HEATMAP <<
Resource Name | Primary Skill | Manager | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01
Mike | Java Fullstack | Director B | 3.5 | 3.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sarah | Data Engineering | Director B | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Jessica | Python/AI | Director A | 3.5 | 3.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tom | Python/AI | Director B | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Ravi | Java Fullstack | Director A | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Siva | Java Fullstack | Director B | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Wei | Java Fullstack | Director A | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lisa | Data Engineering | Director A | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
John | SAP ABAP | Director A | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Priya | Python/AI | Director A | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## DB_Config (hidden)
Quarters
Q1-2026
Q2-2026
Q3-2026
Q4-2026
Q1-2027
Q2-2027
Q3-2027
Q4-2027
Q1-2028
Q2-2028
Q3-2028
Q4-2028
Q1-2029
Q2-2029
Q3-2029
Q4-2029
Q1-2030
Q2-2030
Q3-2030
Q4-2030
Q1-2031
Q2-2031
Q3-2031
Q4-2031
Q1-2032
Q2-2032
Q3-2032
Q4-2032
Q1-2033
Q2-2033
Q3-2033
Q4-2033

## DB_Projects
Project_ID | Project_Name | Portfolio | Team | Goal | Lead | PM | Kickoff | End_Date
P001 | Project B-01 | Cloud Infra | Squad Beta | Q2-2027 | Suresh | Kalpesh | 2026-01-02 | 2026-07-01
P002 | Project C-02 | Digital Transformation | Core Ops | Q4-2031 | Brandi | Kalpesh | 2026-01-02 | 2026-07-01
P003 | Project D-03 | Data & AI | Core Ops | Q2-2027 | Stanley | Kalpesh | 2026-01-02 | 2026-07-01
P004 | Project E-04 | Legacy Modernization | Core Ops | Q3-2032 | Brandi | Rail | 2026-01-02 | 2026-07-01
P005 | Project F-05 | Legacy Modernization | Squad Gamma | Q3-2027 | Abhi | Kalpesh | 2026-01-02 | 2026-07-01
P006 | Project G-06 | Cloud Infra | Squad Beta | Q3-2027 | Abhi | Rail | 2026-01-02 | 2026-07-01
P007 | Project H-07 | Digital Transformation | Squad Gamma | Q4-2029 | Abhi | Rail | 2026-01-02 | 2026-07-01
P008 | Project I-08 | Digital Transformation | Squad Alpha | Q3-2033 | Suresh | Kalpesh | 2026-01-02 | 2026-07-01
P009 | Project J-09 | Cloud Infra | Core Ops | Q4-2032 | Suresh | Rail | 2026-01-02 | 2026-07-01
P010 | Project K-10 | Legacy Modernization | Core Ops | Q2-2031 | Brandi | Rail | 2026-01-02 | 2026-07-01
P011 | Project L-11 | Cloud Infra | Core Ops | Q4-2026 | Stanley | Rail | 2026-01-02 | 2026-07-01
P012 | Project M-12 | Digital Transformation | Squad Beta | Q3-2032 | Abhi | Kalpesh | 2026-01-02 | 2026-07-01
P013 | Project N-13 | Data & AI | Squad Alpha | Q4-2030 | Stanley | Rail | 2026-01-02 | 2026-07-01
P014 | Project O-14 | Digital Transformation | Squad Alpha | Q4-2026 | Abhi | Kalpesh | 2026-01-02 | 2026-07-01
P015 | Project P-15 | Legacy Modernization | Squad Alpha | Q3-2029 | Abhi | Kalpesh | 2026-01-02 | 2026-07-01
P016 | Project Q-16 | Data & AI | Core Ops | Q3-2027 | Stanley | Rail | 2026-01-02 | 2026-07-01
P017 | Project R-17 | Data & AI | Squad Beta | Q2-2027 | Brandi | Rail | 2026-01-02 | 2026-07-01
P018 | Project S-18 | Digital Transformation | Squad Beta | Q1-2030 | Abhi | Rail | 2026-01-02 | 2026-07-01
P019 | Project T-19 | Digital Transformation | Core Ops | Q1-2029 | Suresh | Kalpesh | 2026-01-02 | 2026-07-01
P020 | Project U-20 | Cloud Infra | Core Ops | Q1-2030 | Brandi | Kalpesh | 2026-01-02 | 2026-07-01
P021 | Project V-21 | Legacy Modernization | Squad Gamma | Q2-2029 | Brandi | Kalpesh | 2026-01-02 | 2026-07-01
P022 | Project W-22 | Cloud Infra | Squad Alpha | Q3-2030 | Brandi | Kalpesh | 2026-01-02 | 2026-07-01
P023 | Project X-23 | Legacy Modernization | Squad Beta | Q4-2027 | Abhi | Rail | 2026-01-02 | 2026-07-01
P024 | Project Y-24 | Cloud Infra | Squad Beta | Q3-2029 | Suresh | Rail | 2026-01-02 | 2026-07-01
P025 | Project Z-25 | Data & AI | Squad Gamma | Q2-2031 | Abhi | Rail | 2026-01-02 | 2026-07-01

## DB_Resources
Resource_ID | Full_Name | Skill_ID | Skill_Level | Years_Exp | Manager
R000 | Mike | S01 | Senior | 12 | Director B
R001 | Sarah | S04 | Senior | 12 | Director B
R002 | Jessica | S02 | Junior | 9 | Director A
R003 | Tom | S02 | Standard | 8 | Director B
R004 | Ravi | S01 | Senior | 14 | Director A
R005 | Siva | S01 | Standard | 7 | Director B
R006 | Wei | S01 | Junior | 2 | Director A
R007 | Lisa | S04 | Junior | 14 | Director A
R008 | John | S03 | Junior | 15 | Director A
R009 | Priya | S02 | Junior | 3 | Director A

## DB_Skills
Skill_ID | Skill_Name | Levels
S01 | Java Fullstack | L1, L2, L3
S02 | Python/AI | L1, L2, L3
S03 | SAP ABAP | L1, L2, L3
S04 | Data Engineering | L1, L2, L3
S05 | Cloud/DevOps | L1, L2, L3

## DB_Financials
Project_ID | Total_Budget | Actuals_To_Date | Forecast_To_Complete | Budget_Status
P001 | 134000 | 49512 | 84487 | Amber
P002 | 128000 | 41064 | 86935 | Green
P003 | 245000 | 93179 | 151820 | Green
P004 | 303000 | 85112 | 217887 | Amber
P005 | 363000 | 164117 | 198882 | Green
P006 | 345000 | 134347 | 210652 | Green
P007 | 436000 | 94107 | 341892 | Green
P008 | 387000 | 138865 | 248134 | Green
P009 | 463000 | 127148 | 335851 | Amber
P010 | 67000 | 12715 | 54284 | Amber
P011 | 379000 | 116837 | 262162 | Amber
P012 | 79000 | 25218 | 53781 | Green
P013 | 138000 | 28758 | 109241 | Green
P014 | 188000 | 25862 | 162137 | Green
P015 | 345000 | 89753 | 255246 | Green
P016 | 202000 | 87253 | 114746 | Amber
P017 | 361000 | 202942 | 158057 | Amber
P018 | 455000 | 254245 | 200754 | Green
P019 | 282000 | 75950 | 206049 | Green
P020 | 214000 | 70108 | 143891 | Green
P021 | 313000 | 124251 | 188748 | Green
P022 | 255000 | 46267 | 208732 | Green
P023 | 469000 | 64364 | 404635 | Amber
P024 | 207000 | 105113 | 101886 | Green
P025 | 312000 | 101703 | 210296 | Green

## DB_Allocations
Project_ID | Resource_ID | Allocation_% | Start_Date | End_Date
P001 | R008 | 1 | 2026-01-22 | 2026-04-22
P001 | R000 | 0.5 | 2026-01-22 | 2026-04-22
P001 | R006 | 0.5 | 2026-01-22 | 2026-04-22
P002 | R009 | 0.5 | 2026-01-22 | 2026-04-22
P002 | R000 | 1 | 2026-01-22 | 2026-04-22
P002 | R007 | 1 | 2026-01-22 | 2026-04-22
P003 | R004 | 0.5 | 2026-01-22 | 2026-04-22
P003 | R007 | 0.5 | 2026-01-22 | 2026-04-22
P003 | R003 | 0.5 | 2026-01-22 | 2026-04-22
P004 | R006 | 1 | 2026-01-22 | 2026-04-22
P004 | R004 | 0.5 | 2026-01-22 | 2026-04-22
P005 | R001 | 0.5 | 2026-01-22 | 2026-04-22
P005 | R008 | 0.5 | 2026-01-22 | 2026-04-22
P005 | R005 | 1 | 2026-01-22 | 2026-04-22
P006 | R008 | 1 | 2026-01-22 | 2026-04-22
P006 | R007 | 1 | 2026-01-22 | 2026-04-22
P007 | R007 | 1 | 2026-01-22 | 2026-04-22
P007 | R006 | 0.5 | 2026-01-22 | 2026-04-22
P007 | R001 | 1 | 2026-01-22 | 2026-04-22
P008 | R001 | 1 | 2026-01-22 | 2026-04-22
P008 | R005 | 1 | 2026-01-22 | 2026-04-22
P009 | R003 | 0.5 | 2026-01-22 | 2026-04-22
P009 | R006 | 1 | 2026-01-22 | 2026-04-22
P010 | R000 | 1 | 2026-01-22 | 2026-04-22
P010 | R002 | 1 | 2026-01-22 | 2026-04-22
P010 | R001 | 1 | 2026-01-22 | 2026-04-22
P011 | R008 | 1 | 2026-01-22 | 2026-04-22
P011 | R001 | 0.5 | 2026-01-22 | 2026-04-22
P011 | R003 | 0.5 | 2026-01-22 | 2026-04-22
P012 | R008 | 1 | 2026-01-22 | 2026-04-22
P012 | R009 | 1 | 2026-01-22 | 2026-04-22
P013 | R000 | 1 | 2026-01-22 | 2026-04-22
P013 | R004 | 1 | 2026-01-22 | 2026-04-22
P014 | R005 | 1 | 2026-01-22 | 2026-04-22
P014 | R007 | 0.5 | 2026-01-22 | 2026-04-22
P014 | R001 | 0.5 | 2026-01-22 | 2026-04-22
P015 | R009 | 1 | 2026-01-22 | 2026-04-22
P015 | R008 | 1 | 2026-01-22 | 2026-04-22
P016 | R003 | 1 | 2026-01-22 | 2026-04-22
P016 | R001 | 1 | 2026-01-22 | 2026-04-22
P016 | R008 | 1 | 2026-01-22 | 2026-04-22
P017 | R001 | 0.5 | 2026-01-22 | 2026-04-22
P017 | R007 | 1 | 2026-01-22 | 2026-04-22
P018 | R004 | 0.5 | 2026-01-22 | 2026-04-22
P018 | R009 | 0.5 | 2026-01-22 | 2026-04-22
P019 | R008 | 1 | 2026-01-22 | 2026-04-22
P019 | R001 | 1 | 2026-01-22 | 2026-04-22
P019 | R006 | 0.5 | 2026-01-22 | 2026-04-22
P020 | R008 | 1 | 2026-01-22 | 2026-04-22
P020 | R004 | 0.5 | 2026-01-22 | 2026-04-22
P021 | R008 | 1 | 2026-01-22 | 2026-04-22
P021 | R004 | 1 | 2026-01-22 | 2026-04-22
P021 | R007 | 0.5 | 2026-01-22 | 2026-04-22
P022 | R002 | 0.5 | 2026-01-22 | 2026-04-22
P022 | R006 | 0.5 | 2026-01-22 | 2026-04-22
P022 | R008 | 0.5 | 2026-01-22 | 2026-04-22
P023 | R001 | 1 | 2026-01-22 | 2026-04-22
P023 | R002 | 1 | 2026-01-22 | 2026-04-22
P023 | R006 | 1 | 2026-01-22 | 2026-04-22
P024 | R003 | 0.5 | 2026-01-22 | 2026-04-22
P024 | R007 | 0.5 | 2026-01-22 | 2026-04-22
P024 | R001 | 1 | 2026-01-22 | 2026-04-22
P025 | R002 | 1 | 2026-01-22 | 2026-04-22
P025 | R003 | 1 | 2026-01-22 | 2026-04-22

## DB_Pipeline
Pipeline_ID | Project_ID | Portfolio | Team | Goal | Skill_ID | Skill_Level_Needed | Start_Date | End_Date | Solution_Architect | Product_Owner | LTIM_Lead
PIPE-001 | NEW-PROJ-1 | Data & AI | Squad Alpha | Q1-2026 | S04 | Senior | 2026-01-01 | 2026-05-01 | TBD | TBD | TBD
PIPE-002 | NEW-PROJ-2 | Legacy Modernization | Squad Alpha | Q4-2030 | S05 | Senior | 2026-05-01 | 2027-01-01 | TBD | TBD | TBD
PIPE-003 | NEW-PROJ-3 | Legacy Modernization | Squad Beta | Q2-2029 | S05 | Standard | 2026-06-01 | 2026-09-01 | TBD | TBD | TBD
PIPE-004 | NEW-PROJ-4 | Legacy Modernization | Core Ops | Q3-2032 | S05 | Senior | 2026-01-01 | 2026-09-01 | TBD | TBD | TBD
PIPE-005 | NEW-PROJ-5 | Cloud Infra | Squad Alpha | Q3-2030 | S03 | Standard | 2027-06-01 | 2027-10-01 | TBD | TBD | TBD
PIPE-006 | NEW-PROJ-6 | Cloud Infra | Squad Beta | Q2-2030 | S02 | Standard | 2027-05-01 | 2028-01-01 | TBD | TBD | TBD
PIPE-007 | NEW-PROJ-7 | Cloud Infra | Core Ops | Q3-2033 | S01 | Standard | 2027-06-01 | 2027-11-01 | TBD | TBD | TBD
PIPE-008 | NEW-PROJ-8 | Legacy Modernization | Squad Alpha | Q1-2029 | S01 | Standard | 2027-05-01 | 2027-09-01 | TBD | TBD | TBD
PIPE-009 | NEW-PROJ-9 | Legacy Modernization | Core Ops | Q1-2027 | S01 | Senior | 2027-10-01 | 2028-04-01 | TBD | TBD | TBD
PIPE-010 | NEW-PROJ-10 | Legacy Modernization | Squad Beta | Q2-2032 | S03 | Senior | 2027-06-01 | 2028-01-01 | TBD | TBD | TBD
PIPE-011 | NEW-PROJ-11 | Digital Transformation | Squad Alpha | Q4-2031 | S03 | Standard | 2026-12-01 | 2027-08-01 | TBD | TBD | TBD
PIPE-012 | NEW-PROJ-12 | Digital Transformation | Squad Alpha | Q3-2026 | S02 | Senior | 2026-01-01 | 2026-08-01 | TBD | TBD | TBD
PIPE-013 | NEW-PROJ-13 | Digital Transformation | Squad Gamma | Q3-2030 | S05 | Senior | 2027-06-01 | 2027-12-01 | TBD | TBD | TBD
PIPE-014 | NEW-PROJ-14 | Digital Transformation | Core Ops | Q1-2029 | S01 | Standard | 2027-04-01 | 2028-01-01 | TBD | TBD | TBD
PIPE-015 | NEW-PROJ-15 | Legacy Modernization | Squad Alpha | Q2-2028 | S02 | Standard | 2026-01-01 | 2026-10-01 | TBD | TBD | TBD
PIPE-016 | NEW-PROJ-16 | Cloud Infra | Squad Alpha | Q2-2027 | S01 | Senior | 2027-07-01 | 2028-01-01 | TBD | TBD | TBD
PIPE-017 | NEW-PROJ-17 | Data & AI | Core Ops | Q1-2032 | S02 | Standard | 2027-10-01 | 2028-07-01 | TBD | TBD | TBD
PIPE-018 | NEW-PROJ-18 | Cloud Infra | Squad Gamma | Q2-2028 | S04 | Standard | 2026-06-01 | 2027-03-01 | TBD | TBD | TBD
PIPE-019 | NEW-PROJ-19 | Cloud Infra | Squad Alpha | Q4-2033 | S04 | Standard | 2026-01-01 | 2026-09-01 | TBD | TBD | TBD
PIPE-020 | NEW-PROJ-20 | Cloud Infra | Squad Gamma | Q1-2030 | S04 | Standard | 2027-10-01 | 2028-01-01 | TBD | TBD | TBD
PIPE-021 | NEW-PROJ-21 | Legacy Modernization | Squad Gamma | Q2-2033 | S04 | Standard | 2027-09-01 | 2028-02-01 | TBD | TBD | TBD
PIPE-022 | NEW-PROJ-22 | Legacy Modernization | Squad Beta | Q3-2029 | S03 | Senior | 2026-07-01 | 2027-02-01 | TBD | TBD | TBD
PIPE-023 | NEW-PROJ-23 | Legacy Modernization | Squad Beta | Q3-2027 | S01 | Senior | 2026-05-01 | 2027-01-01 | TBD | TBD | TBD
PIPE-024 | NEW-PROJ-24 | Digital Transformation | Squad Beta | Q1-2032 | S01 | Standard | 2027-02-01 | 2027-05-01 | TBD | TBD | TBD
PIPE-025 | NEW-PROJ-25 | Digital Transformation | Squad Gamma | Q2-2029 | S03 | Standard | 2026-06-01 | 2027-03-01 | TBD | TBD | TBD
PIPE-026 | NEW-PROJ-26 | Legacy Modernization | Core Ops | Q4-2029 | S04 | Standard | 2026-05-01 | 2026-10-01 | TBD | TBD | TBD
PIPE-027 | NEW-PROJ-27 | Digital Transformation | Core Ops | Q2-2032 | S02 | Standard | 2026-08-01 | 2027-04-01 | TBD | TBD | TBD
PIPE-028 | NEW-PROJ-28 | Legacy Modernization | Squad Alpha | Q1-2027 | S04 | Senior | 2026-01-01 | 2026-04-01 | TBD | TBD | TBD
PIPE-029 | NEW-PROJ-29 | Data & AI | Squad Alpha | Q4-2031 | S02 | Senior | 2026-01-01 | 2026-04-01 | TBD | TBD | TBD
PIPE-030 | NEW-PROJ-30 | Digital Transformation | Squad Beta | Q4-2026 | S04 | Senior | 2027-08-01 | 2027-12-01 | TBD | TBD | TBD

## DB_Milestones
Project_ID | Milestone | Baseline_Date | Forecast_Date | Progress_Pct | Status | Comments | Risks_Issues
P001 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P001 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None
P002 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P002 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None
P003 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P003 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None
P004 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P004 | Build | 2026-04-10 | 2026-04-25 | 0.4 | Delayed | In Progress | None
P005 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P005 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None
P006 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P006 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None
P007 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P007 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None
P008 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P008 | Build | 2026-04-10 | 2026-04-25 | 0.4 | Delayed | In Progress | None
P009 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P009 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None
P010 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P010 | Build | 2026-04-10 | 2026-04-25 | 0.4 | Delayed | In Progress | None
P011 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P011 | Build | 2026-04-10 | 2026-04-25 | 0.4 | Delayed | In Progress | None
P012 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P012 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None
P013 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P013 | Build | 2026-04-10 | 2026-04-25 | 0.4 | Delayed | In Progress | None
P014 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P014 | Build | 2026-04-10 | 2026-04-25 | 0.4 | Delayed | In Progress | None
P015 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P015 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None
P016 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P016 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None
P017 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P017 | Build | 2026-04-10 | 2026-04-25 | 0.4 | Delayed | In Progress | None
P018 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P018 | Build | 2026-04-10 | 2026-04-25 | 0.4 | Delayed | In Progress | None
P019 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P019 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None
P020 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P020 | Build | 2026-04-10 | 2026-04-25 | 0.4 | Delayed | In Progress | None
P021 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P021 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None
P022 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P022 | Build | 2026-04-10 | 2026-04-25 | 0.4 | Delayed | In Progress | None
P023 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P023 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None
P024 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P024 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None
P025 | Discovery | 2026-02-15 | 2026-02-15 | 1 | Completed | Done | None
P025 | Build | 2026-04-10 | 2026-04-10 | 0.4 | On Track | In Progress | None

## DB_Updates
Project_ID | Week | RAG | Goal | Narrative | Tasks | Risks
P001 | Wk 05 | Red | Finalize UAT | Critical delay | 1. Task A 2. Task B | Staffing
P002 | Wk 05 | Amber | Finalize UAT | Steady progress | 1. Task A 2. Task B | Staffing
P003 | Wk 05 | Green | Finalize UAT | Steady progress | 1. Task A 2. Task B | None
P004 | Wk 05 | Amber | Finalize UAT | Steady progress | 1. Task A 2. Task B | Staffing
P005 | Wk 05 | Green | Finalize UAT | Steady progress | 1. Task A 2. Task B | None
P006 | Wk 05 | Amber | Finalize UAT | Steady progress | 1. Task A 2. Task B | Staffing
P007 | Wk 05 | Amber | Finalize UAT | Steady progress | 1. Task A 2. Task B | Staffing
P008 | Wk 05 | Amber | Finalize UAT | Steady progress | 1. Task A 2. Task B | Staffing
P009 | Wk 05 | Red | Finalize UAT | Critical delay | 1. Task A 2. Task B | Staffing
P010 | Wk 05 | Red | Finalize UAT | Critical delay | 1. Task A 2. Task B | Staffing
P011 | Wk 05 | Amber | Finalize UAT | Steady progress | 1. Task A 2. Task B | Staffing
P012 | Wk 05 | Red | Finalize UAT | Critical delay | 1. Task A 2. Task B | Staffing
P013 | Wk 05 | Amber | Finalize UAT | Steady progress | 1. Task A 2. Task B | Staffing
P014 | Wk 05 | Amber | Finalize UAT | Steady progress | 1. Task A 2. Task B | Staffing
P015 | Wk 05 | Green | Finalize UAT | Steady progress | 1. Task A 2. Task B | None
P016 | Wk 05 | Amber | Finalize UAT | Steady progress | 1. Task A 2. Task B | Staffing
P017 | Wk 05 | Red | Finalize UAT | Critical delay | 1. Task A 2. Task B | Staffing
P018 | Wk 05 | Green | Finalize UAT | Steady progress | 1. Task A 2. Task B | None
P019 | Wk 05 | Amber | Finalize UAT | Steady progress | 1. Task A 2. Task B | Staffing
P020 | Wk 05 | Green | Finalize UAT | Steady progress | 1. Task A 2. Task B | None
P021 | Wk 05 | Amber | Finalize UAT | Steady progress | 1. Task A 2. Task B | Staffing
P022 | Wk 05 | Amber | Finalize UAT | Steady progress | 1. Task A 2. Task B | Staffing
P023 | Wk 05 | Amber | Finalize UAT | Steady progress | 1. Task A 2. Task B | Staffing
P024 | Wk 05 | Red | Finalize UAT | Critical delay | 1. Task A 2. Task B | Staffing
P025 | Wk 05 | Amber | Finalize UAT | Steady progress | 1. Task A 2. Task B | Staffing

## DB_SLA
Project_ID | Metric | Status
P001 | Defect SLA | Met
P002 | Defect SLA | Met
P003 | Defect SLA | Met
P004 | Defect SLA | Met
P005 | Defect SLA | Met
P006 | Defect SLA | Met
P007 | Defect SLA | Met
P008 | Defect SLA | Met
P009 | Defect SLA | Met
P010 | Defect SLA | Met
P011 | Defect SLA | Met
P012 | Defect SLA | Met
P013 | Defect SLA | Met
P014 | Defect SLA | Met
P015 | Defect SLA | Met
P016 | Defect SLA | Met
P017 | Defect SLA | Met
P018 | Defect SLA | Met
P019 | Defect SLA | Met
P020 | Defect SLA | Met
P021 | Defect SLA | Met
P022 | Defect SLA | Met
P023 | Defect SLA | Met
P024 | Defect SLA | Met
P025 | Defect SLA | Met