## >> DASHBOARD <<
Project Name | Portfolio | Team | Lead / PM | Overall Status | Milestone Roadmap | Resource Plan | Total FTE | Weekly Update | SLA
Project G-06 | Cloud Infra | Core Ops | Lead: Abhi PM: Sigmas | Green | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Wei (Python/AI): 50% [Mar-Jun] • Mike (Java Fullstack): 50% [Mar-Aug] • John (Data Eng): 50% [Dec-Mar] | 1.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: None | Breached
Project I-08 | Cloud Infra | Squad Alpha | Lead: Stanley PM: Rail | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Tom (Data Eng): 50% [Jan-May] • John (Data Eng): 50% [Feb-May] | 1 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Critical path delayed due to API. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Breached
Project U-20 | Cloud Infra | Squad Alpha | Lead: Stanley PM: Rail | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Wei (Python/AI): 100% [Dec-Jun] • Siva (Java Fullstack): 50% [Jan-Jun] • Sarah (Python/AI): 100% [Jan-May] | 2.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Critical path delayed due to API. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Breached
Project M-12 | Cloud Infra | Squad Beta | Lead: Stanley PM: Sigmas | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Jessica (SAP ABAP): 100% [Jan-Jun] • Mike (Java Fullstack): 50% [Mar-Jun] | 1.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Met
Project T-19 | Data & AI | Core Ops | Lead: Suresh PM: Kalpesh | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Tom (Data Eng): 50% [Feb-Jul] • Sarah (Python/AI): 50% [Mar-Jun] • Mike (Java Fullstack): 50% [Jan-Apr] | 1.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Critical path delayed due to API. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Breached
Project E-04 | Data & AI | Squad Alpha | Lead: Brandi PM: Kalpesh | Green | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Wei (Python/AI): 50% [Dec-Apr] • Mike (Java Fullstack): 50% [Feb-Jun] | 1 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: None | Met
Project X-23 | Data & AI | Squad Beta | Lead: Stanley PM: Rail | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • John (Data Eng): 50% [Jan-Apr] • Priya (DevOps): 50% [Mar-Jun] | 1 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Critical path delayed due to API. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Breached
Project Z-25 | Data & AI | Squad Beta | Lead: Stanley PM: Sigmas | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Priya (DevOps): 50% [Dec-Jun] • Sarah (Python/AI): 100% [Jan-Jun] | 1.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Met
Project D-03 | Data & AI | Squad Gamma | Lead: Brandi PM: Sigmas | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Ravi (DevOps): 50% [Jan-May] • Wei (Python/AI): 50% [Jan-Apr] | 1 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Critical path delayed due to API. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Met
Project H-07 | Data & AI | Squad Gamma | Lead: Stanley PM: Kalpesh | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Wei (Python/AI): 50% [Mar-Aug] • Tom (Data Eng): 100% [Feb-May] | 1.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Met
Project N-13 | Data & AI | Squad Gamma | Lead: Suresh PM: Rail | Green | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • John (Data Eng): 100% [Jan-Apr] • Tom (Data Eng): 50% [Feb-Jul] • Lisa (SAP ABAP): 50% [Dec-Jun] | 2 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: None | Met
Project V-21 | Data & AI | Squad Gamma | Lead: Stanley PM: Sigmas | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Sarah (Python/AI): 50% [Jan-Apr] • Ravi (DevOps): 100% [Feb-Jul] • Wei (Python/AI): 50% [Mar-Jun] | 2 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Critical path delayed due to API. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Met
Project F-05 | Digital Transformation | Core Ops | Lead: Stanley PM: Sigmas | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Lisa (SAP ABAP): 50% [Mar-Aug] • Mike (Java Fullstack): 50% [Jan-May] • Tom (Data Eng): 50% [Feb-Jun] | 1.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Met
Project P-15 | Digital Transformation | Core Ops | Lead: Stanley PM: Sigmas | Green | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Priya (DevOps): 100% [Jan-May] • Tom (Data Eng): 50% [Feb-Aug] | 1.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: None | Breached
Project L-11 | Digital Transformation | Squad Alpha | Lead: Suresh PM: Sigmas | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Mike (Java Fullstack): 50% [Mar-Aug] • John (Data Eng): 50% [Dec-Mar] | 1 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Critical path delayed due to API. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Met
Project B-01 | Digital Transformation | Squad Beta | Lead: Abhi PM: Sigmas | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Jessica (SAP ABAP): 50% [Mar-Sep] • Tom (Data Eng): 50% [Dec-Jun] | 1 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Critical path delayed due to API. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Breached
Project C-02 | Digital Transformation | Squad Gamma | Lead: Stanley PM: Kalpesh | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Wei (Python/AI): 50% [Dec-Mar] • Lisa (SAP ABAP): 50% [Mar-Aug] • Jessica (SAP ABAP): 50% [Jan-Jun] | 1.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Breached
Project R-17 | Digital Transformation | Squad Gamma | Lead: Brandi PM: Sigmas | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Ravi (DevOps): 100% [Dec-Apr] • John (Data Eng): 100% [Jan-Apr] • Wei (Python/AI): 100% [Mar-Sep] | 3 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Met
Project Y-24 | Digital Transformation | Squad Gamma | Lead: Suresh PM: Rail | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Lisa (SAP ABAP): 50% [Jan-Jul] • Wei (Python/AI): 50% [Feb-Jul] • Jessica (SAP ABAP): 100% [Feb-Jun] | 2 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Critical path delayed due to API. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Met
Project Q-16 | Legacy Modernization | Core Ops | Lead: Abhi PM: Sigmas | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Wei (Python/AI): 50% [Mar-Sep] • Ravi (DevOps): 100% [Mar-Aug] • Priya (DevOps): 50% [Dec-Apr] | 2 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Breached
Project W-22 | Legacy Modernization | Core Ops | Lead: Abhi PM: Kalpesh | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • John (Data Eng): 100% [Feb-Jul] • Mike (Java Fullstack): 50% [Mar-Aug] • Ravi (DevOps): 100% [Dec-Apr] | 2.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Met
Project K-10 | Legacy Modernization | Squad Alpha | Lead: Suresh PM: Sigmas | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Sarah (Python/AI): 50% [Jan-Jul] • Mike (Java Fullstack): 50% [Jan-May] • Ravi (DevOps): 100% [Mar-Jul] | 2 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Breached
Project O-14 | Legacy Modernization | Squad Alpha | Lead: Abhi PM: Kalpesh | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Sarah (Python/AI): 100% [Mar-Jun] • Siva (Java Fullstack): 50% [Dec-Apr] | 1.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Met
Project S-18 | Legacy Modernization | Squad Alpha | Lead: Suresh PM: Sigmas | Green | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Wei (Python/AI): 100% [Feb-May] • Ravi (DevOps): 100% [Mar-Jul] • Mike (Java Fullstack): 100% [Feb-Jun] | 3 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: None | Breached
Project J-09 | Legacy Modernization | Squad Gamma | Lead: Brandi PM: Kalpesh | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Mike (Java Fullstack): 50% [Mar-Jul] • Siva (Java Fullstack): 50% [Mar-Sep] • Priya (DevOps): 50% [Dec-Mar] | 1.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: On track. TASKS: 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA RISK: Resource constraint | Met

## >> RES_HEATMAP <<
Resource Name | Primary Skill | Manager | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Mike | Java Fullstack | Director C | 1.5 | 3 | 5.5 | 5.5 | 5 | 4 | 2 | 1.5 | 0 | 0 | 0 | 0
Sarah | Python/AI | Director B | 3 | 3 | 4.5 | 4.5 | 4 | 3 | 0.5 | 0 | 0 | 0 | 0 | 0
Jessica | SAP ABAP | Director C | 1.5 | 2.5 | 3 | 3 | 3 | 3 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Tom | Data Eng | Director A | 1 | 4 | 4 | 4 | 4 | 2.5 | 1.5 | 0.5 | 0 | 0 | 0 | 0
Ravi | DevOps | Director A | 2.5 | 3.5 | 6.5 | 6.5 | 4.5 | 4 | 4 | 1 | 0 | 0 | 0 | 0
Siva | Java Fullstack | Director B | 1 | 1 | 1.5 | 1.5 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
Wei | Python/AI | Director B | 2.5 | 4 | 7 | 6.5 | 5.5 | 4.5 | 2.5 | 2 | 1.5 | 0 | 0 | 0
Lisa | SAP ABAP | Director A | 1 | 1 | 2 | 2 | 2 | 2 | 1.5 | 1 | 0 | 0 | 0 | 0
John | Data Eng | Director A | 3.5 | 5 | 5 | 4 | 1.5 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Priya | DevOps | Director C | 2.5 | 2.5 | 3 | 2.5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0

## DB_Projects
Project_ID | Project_Name | Portfolio | Team | Lead | PM | Kickoff_Date | End_Date
P001 | Project B-01 | Digital Transformation | Squad Beta | Abhi | Sigmas | 2025-12-07 | 2026-05-24
P002 | Project C-02 | Digital Transformation | Squad Gamma | Stanley | Kalpesh | 2025-12-22 | 2026-05-12
P003 | Project D-03 | Data & AI | Squad Gamma | Brandi | Sigmas | 2025-12-27 | 2026-05-27
P004 | Project E-04 | Data & AI | Squad Alpha | Brandi | Kalpesh | 2025-12-31 | 2026-06-15
P005 | Project F-05 | Digital Transformation | Core Ops | Stanley | Sigmas | 2025-10-21 | 2026-07-28
P006 | Project G-06 | Cloud Infra | Core Ops | Abhi | Sigmas | 2025-11-05 | 2026-04-01
P007 | Project H-07 | Data & AI | Squad Gamma | Stanley | Kalpesh | 2025-11-18 | 2026-05-03
P008 | Project I-08 | Cloud Infra | Squad Alpha | Stanley | Rail | 2025-11-02 | 2026-04-30
P009 | Project J-09 | Legacy Modernization | Squad Gamma | Brandi | Kalpesh | 2025-12-28 | 2026-06-21
P010 | Project K-10 | Legacy Modernization | Squad Alpha | Suresh | Sigmas | 2026-01-07 | 2026-07-29
P011 | Project L-11 | Digital Transformation | Squad Alpha | Suresh | Sigmas | 2026-01-02 | 2026-07-01
P012 | Project M-12 | Cloud Infra | Squad Beta | Stanley | Sigmas | 2026-01-03 | 2026-08-09
P013 | Project N-13 | Data & AI | Squad Gamma | Suresh | Rail | 2026-01-03 | 2026-06-09
P014 | Project O-14 | Legacy Modernization | Squad Alpha | Abhi | Kalpesh | 2025-12-24 | 2026-04-02
P015 | Project P-15 | Digital Transformation | Core Ops | Stanley | Sigmas | 2025-12-02 | 2026-04-28
P016 | Project Q-16 | Legacy Modernization | Core Ops | Abhi | Sigmas | 2025-10-27 | 2026-03-30
P017 | Project R-17 | Digital Transformation | Squad Gamma | Brandi | Sigmas | 2025-12-12 | 2026-05-03
P018 | Project S-18 | Legacy Modernization | Squad Alpha | Suresh | Sigmas | 2025-12-26 | 2026-08-02
P019 | Project T-19 | Data & AI | Core Ops | Suresh | Kalpesh | 2025-12-09 | 2026-07-29
P020 | Project U-20 | Cloud Infra | Squad Alpha | Stanley | Rail | 2025-11-06 | 2026-04-05
P021 | Project V-21 | Data & AI | Squad Gamma | Stanley | Sigmas | 2025-10-26 | 2026-08-05
P022 | Project W-22 | Legacy Modernization | Core Ops | Abhi | Kalpesh | 2025-11-27 | 2026-08-11
P023 | Project X-23 | Data & AI | Squad Beta | Stanley | Rail | 2025-12-02 | 2026-06-24
P024 | Project Y-24 | Digital Transformation | Squad Gamma | Suresh | Rail | 2025-12-23 | 2026-04-26
P025 | Project Z-25 | Data & AI | Squad Beta | Stanley | Sigmas | 2026-01-09 | 2026-05-16

## DB_Resources
Resource_ID | Full_Name | Primary_Skill | Team | Manager
R000 | Mike | Java Fullstack | Digital Squad A | Director C
R001 | Sarah | Python/AI | Core Systems | Director B
R002 | Jessica | SAP ABAP | Digital Squad A | Director C
R003 | Tom | Data Eng | Core Systems | Director A
R004 | Ravi | DevOps | Digital Squad A | Director A
R005 | Siva | Java Fullstack | Core Systems | Director B
R006 | Wei | Python/AI | Digital Squad A | Director B
R007 | Lisa | SAP ABAP | Core Systems | Director A
R008 | John | Data Eng | Digital Squad A | Director A
R009 | Priya | DevOps | Core Systems | Director C

## DB_Allocations
Project_ID | Resource_ID | Allocation_% | Start_Date | End_Date
P001 | R002 | 0.5 | 2026-03-01 | 2026-09-01
P001 | R003 | 0.5 | 2025-12-01 | 2026-06-01
P002 | R006 | 0.5 | 2025-12-01 | 2026-03-01
P002 | R007 | 0.5 | 2026-03-01 | 2026-08-01
P002 | R002 | 0.5 | 2026-01-01 | 2026-06-01
P003 | R004 | 0.5 | 2026-01-01 | 2026-05-01
P003 | R006 | 0.5 | 2026-01-01 | 2026-04-01
P004 | R006 | 0.5 | 2025-12-01 | 2026-04-01
P004 | R000 | 0.5 | 2026-02-01 | 2026-06-01
P005 | R007 | 0.5 | 2026-03-01 | 2026-08-01
P005 | R000 | 0.5 | 2026-01-01 | 2026-05-01
P005 | R003 | 0.5 | 2026-02-01 | 2026-06-01
P006 | R006 | 0.5 | 2026-03-01 | 2026-06-01
P006 | R000 | 0.5 | 2026-03-01 | 2026-08-01
P006 | R008 | 0.5 | 2025-12-01 | 2026-03-01
P007 | R006 | 0.5 | 2026-03-01 | 2026-08-01
P007 | R003 | 1 | 2026-02-01 | 2026-05-01
P008 | R003 | 0.5 | 2026-01-01 | 2026-05-01
P008 | R008 | 0.5 | 2026-02-01 | 2026-05-01
P009 | R000 | 0.5 | 2026-03-01 | 2026-07-01
P009 | R005 | 0.5 | 2026-03-01 | 2026-09-01
P009 | R009 | 0.5 | 2025-12-01 | 2026-03-01
P010 | R001 | 0.5 | 2026-01-01 | 2026-07-01
P010 | R000 | 0.5 | 2026-01-01 | 2026-05-01
P010 | R004 | 1 | 2026-03-01 | 2026-07-01
P011 | R000 | 0.5 | 2026-03-01 | 2026-08-01
P011 | R008 | 0.5 | 2025-12-01 | 2026-03-01
P012 | R002 | 1 | 2026-01-01 | 2026-06-01
P012 | R000 | 0.5 | 2026-03-01 | 2026-06-01
P013 | R008 | 1 | 2026-01-01 | 2026-04-01
P013 | R003 | 0.5 | 2026-02-01 | 2026-07-01
P013 | R007 | 0.5 | 2025-12-01 | 2026-06-01
P014 | R001 | 1 | 2026-03-01 | 2026-06-01
P014 | R005 | 0.5 | 2025-12-01 | 2026-04-01
P015 | R009 | 1 | 2026-01-01 | 2026-05-01
P015 | R003 | 0.5 | 2026-02-01 | 2026-08-01
P016 | R006 | 0.5 | 2026-03-01 | 2026-09-01
P016 | R004 | 1 | 2026-03-01 | 2026-08-01
P016 | R009 | 0.5 | 2025-12-01 | 2026-04-01
P017 | R004 | 1 | 2025-12-01 | 2026-04-01
P017 | R008 | 1 | 2026-01-01 | 2026-04-01
P017 | R006 | 1 | 2026-03-01 | 2026-09-01
P018 | R006 | 1 | 2026-02-01 | 2026-05-01
P018 | R004 | 1 | 2026-03-01 | 2026-07-01
P018 | R000 | 1 | 2026-02-01 | 2026-06-01
P019 | R003 | 0.5 | 2026-02-01 | 2026-07-01
P019 | R001 | 0.5 | 2026-03-01 | 2026-06-01
P019 | R000 | 0.5 | 2026-01-01 | 2026-04-01
P020 | R006 | 1 | 2025-12-01 | 2026-06-01
P020 | R005 | 0.5 | 2026-01-01 | 2026-06-01
P020 | R001 | 1 | 2026-01-01 | 2026-05-01
P021 | R001 | 0.5 | 2026-01-01 | 2026-04-01
P021 | R004 | 1 | 2026-02-01 | 2026-07-01
P021 | R006 | 0.5 | 2026-03-01 | 2026-06-01
P022 | R008 | 1 | 2026-02-01 | 2026-07-01
P022 | R000 | 0.5 | 2026-03-01 | 2026-08-01
P022 | R004 | 1 | 2025-12-01 | 2026-04-01
P023 | R008 | 0.5 | 2026-01-01 | 2026-04-01
P023 | R009 | 0.5 | 2026-03-01 | 2026-06-01
P024 | R007 | 0.5 | 2026-01-01 | 2026-07-01
P024 | R006 | 0.5 | 2026-02-01 | 2026-07-01
P024 | R002 | 1 | 2026-02-01 | 2026-06-01
P025 | R009 | 0.5 | 2025-12-01 | 2026-06-01
P025 | R001 | 1 | 2026-01-01 | 2026-06-01

## DB_Updates
Project_ID | Week | RAG | Goal_This_Week | Narrative | Upcoming_Tasks | Risks
P001 | Wk 05 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Critical path delayed due to API. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P002 | Wk 05 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P003 | Wk 05 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Critical path delayed due to API. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P004 | Wk 05 | Green | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | None
P005 | Wk 05 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P006 | Wk 05 | Green | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | None
P007 | Wk 05 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P008 | Wk 05 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Critical path delayed due to API. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P009 | Wk 05 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P010 | Wk 05 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P011 | Wk 05 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Critical path delayed due to API. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P012 | Wk 05 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P013 | Wk 05 | Green | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | None
P014 | Wk 05 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P015 | Wk 05 | Green | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | None
P016 | Wk 05 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P017 | Wk 05 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P018 | Wk 05 | Green | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | None
P019 | Wk 05 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Critical path delayed due to API. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P020 | Wk 05 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Critical path delayed due to API. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P021 | Wk 05 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Critical path delayed due to API. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P022 | Wk 05 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P023 | Wk 05 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Critical path delayed due to API. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P024 | Wk 05 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Critical path delayed due to API. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint
P025 | Wk 05 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | On track. | 1. Finalize API Spec 2. Sign-off UAT Plan 3. Onboard new QA | Resource constraint

## DB_Milestones
Project_ID | Milestone | Date | Status | Completion_Pct
P001 | Discovery | 2026-01-09 | Completed | 1
P001 | Design | 2026-01-29 | Completed | 1
P001 | Build | 2026-02-18 | In Progress | 0.5
P001 | UAT | 2026-03-10 | Pending | 0
P001 | Go-Live | 2026-03-30 | Pending | 0
P002 | Discovery | 2026-01-09 | Completed | 1
P002 | Design | 2026-01-29 | Completed | 1
P002 | Build | 2026-02-18 | In Progress | 0.5
P002 | UAT | 2026-03-10 | Pending | 0
P002 | Go-Live | 2026-03-30 | Pending | 0
P003 | Discovery | 2026-01-09 | Completed | 1
P003 | Design | 2026-01-29 | Completed | 1
P003 | Build | 2026-02-18 | In Progress | 0.5
P003 | UAT | 2026-03-10 | Pending | 0
P003 | Go-Live | 2026-03-30 | Pending | 0
P004 | Discovery | 2026-01-09 | Completed | 1
P004 | Design | 2026-01-29 | Completed | 1
P004 | Build | 2026-02-18 | In Progress | 0.5
P004 | UAT | 2026-03-10 | Pending | 0
P004 | Go-Live | 2026-03-30 | Pending | 0
P005 | Discovery | 2026-01-09 | Completed | 1
P005 | Design | 2026-01-29 | Completed | 1
P005 | Build | 2026-02-18 | In Progress | 0.5
P005 | UAT | 2026-03-10 | Pending | 0
P005 | Go-Live | 2026-03-30 | Pending | 0
P006 | Discovery | 2026-01-09 | Completed | 1
P006 | Design | 2026-01-29 | Completed | 1
P006 | Build | 2026-02-18 | In Progress | 0.5
P006 | UAT | 2026-03-10 | Pending | 0
P006 | Go-Live | 2026-03-30 | Pending | 0
P007 | Discovery | 2026-01-09 | Completed | 1
P007 | Design | 2026-01-29 | Completed | 1
P007 | Build | 2026-02-18 | In Progress | 0.5
P007 | UAT | 2026-03-10 | Pending | 0
P007 | Go-Live | 2026-03-30 | Pending | 0
P008 | Discovery | 2026-01-09 | Completed | 1
P008 | Design | 2026-01-29 | Completed | 1
P008 | Build | 2026-02-18 | In Progress | 0.5
P008 | UAT | 2026-03-10 | Pending | 0
P008 | Go-Live | 2026-03-30 | Pending | 0
P009 | Discovery | 2026-01-09 | Completed | 1
P009 | Design | 2026-01-29 | Completed | 1
P009 | Build | 2026-02-18 | In Progress | 0.5
P009 | UAT | 2026-03-10 | Pending | 0
P009 | Go-Live | 2026-03-30 | Pending | 0
P010 | Discovery | 2026-01-09 | Completed | 1
P010 | Design | 2026-01-29 | Completed | 1
P010 | Build | 2026-02-18 | In Progress | 0.5
P010 | UAT | 2026-03-10 | Pending | 0
P010 | Go-Live | 2026-03-30 | Pending | 0
P011 | Discovery | 2026-01-09 | Completed | 1
P011 | Design | 2026-01-29 | Completed | 1
P011 | Build | 2026-02-18 | In Progress | 0.5
P011 | UAT | 2026-03-10 | Pending | 0
P011 | Go-Live | 2026-03-30 | Pending | 0
P012 | Discovery | 2026-01-09 | Completed | 1
P012 | Design | 2026-01-29 | Completed | 1
P012 | Build | 2026-02-18 | In Progress | 0.5
P012 | UAT | 2026-03-10 | Pending | 0
P012 | Go-Live | 2026-03-30 | Pending | 0
P013 | Discovery | 2026-01-09 | Completed | 1
P013 | Design | 2026-01-29 | Completed | 1
P013 | Build | 2026-02-18 | In Progress | 0.5
P013 | UAT | 2026-03-10 | Pending | 0
P013 | Go-Live | 2026-03-30 | Pending | 0
P014 | Discovery | 2026-01-09 | Completed | 1
P014 | Design | 2026-01-29 | Completed | 1
P014 | Build | 2026-02-18 | In Progress | 0.5
P014 | UAT | 2026-03-10 | Pending | 0
P014 | Go-Live | 2026-03-30 | Pending | 0
P015 | Discovery | 2026-01-09 | Completed | 1
P015 | Design | 2026-01-29 | Completed | 1
P015 | Build | 2026-02-18 | In Progress | 0.5
P015 | UAT | 2026-03-10 | Pending | 0
P015 | Go-Live | 2026-03-30 | Pending | 0
P016 | Discovery | 2026-01-09 | Completed | 1
P016 | Design | 2026-01-29 | Completed | 1
P016 | Build | 2026-02-18 | In Progress | 0.5
P016 | UAT | 2026-03-10 | Pending | 0
P016 | Go-Live | 2026-03-30 | Pending | 0
P017 | Discovery | 2026-01-09 | Completed | 1
P017 | Design | 2026-01-29 | Completed | 1
P017 | Build | 2026-02-18 | In Progress | 0.5
P017 | UAT | 2026-03-10 | Pending | 0
P017 | Go-Live | 2026-03-30 | Pending | 0
P018 | Discovery | 2026-01-09 | Completed | 1
P018 | Design | 2026-01-29 | Completed | 1
P018 | Build | 2026-02-18 | In Progress | 0.5
P018 | UAT | 2026-03-10 | Pending | 0
P018 | Go-Live | 2026-03-30 | Pending | 0
P019 | Discovery | 2026-01-09 | Completed | 1
P019 | Design | 2026-01-29 | Completed | 1
P019 | Build | 2026-02-18 | In Progress | 0.5
P019 | UAT | 2026-03-10 | Pending | 0
P019 | Go-Live | 2026-03-30 | Pending | 0
P020 | Discovery | 2026-01-09 | Completed | 1
P020 | Design | 2026-01-29 | Completed | 1
P020 | Build | 2026-02-18 | In Progress | 0.5
P020 | UAT | 2026-03-10 | Pending | 0
P020 | Go-Live | 2026-03-30 | Pending | 0
P021 | Discovery | 2026-01-09 | Completed | 1
P021 | Design | 2026-01-29 | Completed | 1
P021 | Build | 2026-02-18 | In Progress | 0.5
P021 | UAT | 2026-03-10 | Pending | 0
P021 | Go-Live | 2026-03-30 | Pending | 0
P022 | Discovery | 2026-01-09 | Completed | 1
P022 | Design | 2026-01-29 | Completed | 1
P022 | Build | 2026-02-18 | In Progress | 0.5
P022 | UAT | 2026-03-10 | Pending | 0
P022 | Go-Live | 2026-03-30 | Pending | 0
P023 | Discovery | 2026-01-09 | Completed | 1
P023 | Design | 2026-01-29 | Completed | 1
P023 | Build | 2026-02-18 | In Progress | 0.5
P023 | UAT | 2026-03-10 | Pending | 0
P023 | Go-Live | 2026-03-30 | Pending | 0
P024 | Discovery | 2026-01-09 | Completed | 1
P024 | Design | 2026-01-29 | Completed | 1
P024 | Build | 2026-02-18 | In Progress | 0.5
P024 | UAT | 2026-03-10 | Pending | 0
P024 | Go-Live | 2026-03-30 | Pending | 0
P025 | Discovery | 2026-01-09 | Completed | 1
P025 | Design | 2026-01-29 | Completed | 1
P025 | Build | 2026-02-18 | In Progress | 0.5
P025 | UAT | 2026-03-10 | Pending | 0
P025 | Go-Live | 2026-03-30 | Pending | 0

## DB_SLA
Project_ID | Metric | Status
P001 | Defect Turnaround | Breached
P002 | Defect Turnaround | Breached
P003 | Defect Turnaround | Met
P004 | Defect Turnaround | Met
P005 | Defect Turnaround | Met
P006 | Defect Turnaround | Breached
P007 | Defect Turnaround | Met
P008 | Defect Turnaround | Breached
P009 | Defect Turnaround | Met
P010 | Defect Turnaround | Breached
P011 | Defect Turnaround | Met
P012 | Defect Turnaround | Met
P013 | Defect Turnaround | Met
P014 | Defect Turnaround | Met
P015 | Defect Turnaround | Breached
P016 | Defect Turnaround | Breached
P017 | Defect Turnaround | Met
P018 | Defect Turnaround | Breached
P019 | Defect Turnaround | Breached
P020 | Defect Turnaround | Breached
P021 | Defect Turnaround | Met
P022 | Defect Turnaround | Met
P023 | Defect Turnaround | Breached
P024 | Defect Turnaround | Met
P025 | Defect Turnaround | Met