## >> REPORT <<
WEEKLY EXECUTIVE STATUS REPORT (AUTO-GENERATED)
Project Name | Lead / PM | Overall Status | Milestone Roadmap | Resource Plan | Total Capacity | Weekly Update | SLA
Project B-1 (Stream 2) | Lead: Suresh PM: Sigmas | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Siva (Arch): 100% • Mike (Arch): 100% | 2 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. On track. RISK: None | Breached
Project C-2 (Stream 3) | Lead: Suresh PM: Rail | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Wei (Dev): 100% • Sarah (Dev): 100% • Jessica (QA): 100% | 3 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. On track. RISK: None | Breached
Project D-3 (Stream 1) | Lead: Brandi PM: Rail | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Mike (Arch): 100% • Sarah (Dev): 100% • Tom (BA): 50% • Ravi (Lead): 50% | 3 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. On track. RISK: None | Met
Project E-4 (Stream 2) | Lead: Stanley PM: Sigmas | Green | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Jessica (QA): 100% • Lisa (QA): 100% • Siva (Arch): 50% | 2.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. On track. RISK: None | Breached
Project F-5 (Stream 3) | Lead: Brandi PM: Kalpesh | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Wei (Dev): 25% • Tom (BA): 25% • Jessica (QA): 50% | 1 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. Critical blocker on API. RISK: Data latency issues in QA env | Met
Project G-6 (Stream 1) | Lead: Abhi PM: Sigmas | Green | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Sarah (Dev): 100% • Ravi (Lead): 25% • Siva (Arch): 100% | 2.25 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. On track. RISK: None | Met
Project H-7 (Stream 2) | Lead: Abhi PM: Kalpesh | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Mike (Arch): 100% • Tom (BA): 50% | 1.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. On track. RISK: None | Met
Project I-8 (Stream 3) | Lead: Abhi PM: Rail | Green | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Jessica (QA): 50% • Lisa (QA): 25% • Wei (Dev): 100% | 1.75 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. On track. RISK: None | Met
Project J-9 (Stream 1) | Lead: Suresh PM: Rail | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Siva (Arch): 50% • Jessica (QA): 25% • Wei (Dev): 50% • Mike (Arch): 100% | 2.25 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. Critical blocker on API. RISK: Data latency issues in QA env | Met
Project K-10 (Stream 2) | Lead: Suresh PM: Sigmas | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Lisa (QA): 50% • Sarah (Dev): 25% • Jessica (QA): 25% | 1 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. Critical blocker on API. RISK: Data latency issues in QA env | Met
Project L-11 (Stream 3) | Lead: Stanley PM: Kalpesh | Green | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Sarah (Dev): 100% • Mike (Arch): 50% • Lisa (QA): 100% | 2.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. On track. RISK: None | Met
Project M-12 (Stream 1) | Lead: Suresh PM: Kalpesh | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Tom (BA): 50% • Ravi (Lead): 50% • Sarah (Dev): 100% • Siva (Arch): 100% | 3 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. Critical blocker on API. RISK: Data latency issues in QA env | Met
Project N-13 (Stream 2) | Lead: Suresh PM: Rail | Green | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Wei (Dev): 100% • Lisa (QA): 50% | 1.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. On track. RISK: None | Met
Project O-14 (Stream 3) | Lead: Stanley PM: Sigmas | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Lisa (QA): 25% • Ravi (Lead): 25% | 0.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. Critical blocker on API. RISK: Data latency issues in QA env | Breached
Project P-15 (Stream 1) | Lead: Brandi PM: Rail | Green | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Wei (Dev): 50% • Sarah (Dev): 100% • Mike (Arch): 25% • Jessica (QA): 50% | 2.25 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. On track. RISK: None | Met
Project Q-16 (Stream 2) | Lead: Suresh PM: Sigmas | Green | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Lisa (QA): 25% • Jessica (QA): 100% • Tom (BA): 25% | 1.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. On track. RISK: None | Breached
Project R-17 (Stream 3) | Lead: Suresh PM: Kalpesh | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Wei (Dev): 50% • Tom (BA): 100% | 1.5 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. On track. RISK: None | Breached
Project S-18 (Stream 1) | Lead: Abhi PM: Kalpesh | Red | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Siva (Arch): 100% • Mike (Arch): 50% • Tom (BA): 50% | 2 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. Critical blocker on API. RISK: Data latency issues in QA env | Breached
Project T-19 (Stream 2) | Lead: Suresh PM: Rail | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Tom (BA): 25% • Siva (Arch): 100% • Jessica (QA): 100% • Mike (Arch): 100% | 3.25 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. On track. RISK: None | Met
Project U-20 (Stream 3) | Lead: Suresh PM: Kalpesh | Amber | ✅ Discovery (100%) - 01-09 ✅ Design (100%) - 01-29 ⚠️ Build (50%) - 02-18 ⚪ UAT (0%) - 03-10 ⚪ Go-Live (0%) - 03-30 | • Lisa (QA): 50% • Siva (Arch): 50% • Jessica (QA): 25% | 1.25 | GOAL: Finalize UAT Sign-off and prepare deployment scripts. UPDATE: Progress is steady. On track. RISK: None | Met

## DB_Projects
Project_ID | Project_Name | Lead | PM | Kickoff_Date | End_Date
P001 | Project B-1 (Stream 2) | Suresh | Sigmas | 2025-12-01 | 2026-05-16
P002 | Project C-2 (Stream 3) | Suresh | Rail | 2025-12-15 | 2026-05-07
P003 | Project D-3 (Stream 1) | Brandi | Rail | 2025-11-05 | 2026-06-01
P004 | Project E-4 (Stream 2) | Stanley | Sigmas | 2025-12-29 | 2026-07-08
P005 | Project F-5 (Stream 3) | Brandi | Kalpesh | 2025-11-24 | 2026-05-03
P006 | Project G-6 (Stream 1) | Abhi | Sigmas | 2025-11-04 | 2026-05-25
P007 | Project H-7 (Stream 2) | Abhi | Kalpesh | 2025-12-07 | 2026-06-12
P008 | Project I-8 (Stream 3) | Abhi | Rail | 2025-11-06 | 2026-06-27
P009 | Project J-9 (Stream 1) | Suresh | Rail | 2025-10-25 | 2026-05-20
P010 | Project K-10 (Stream 2) | Suresh | Sigmas | 2025-11-01 | 2026-06-02
P011 | Project L-11 (Stream 3) | Stanley | Kalpesh | 2025-11-27 | 2026-08-05
P012 | Project M-12 (Stream 1) | Suresh | Kalpesh | 2025-11-03 | 2026-06-13
P013 | Project N-13 (Stream 2) | Suresh | Rail | 2025-10-26 | 2026-06-20
P014 | Project O-14 (Stream 3) | Stanley | Sigmas | 2025-11-24 | 2026-04-01
P015 | Project P-15 (Stream 1) | Brandi | Rail | 2025-10-24 | 2026-05-25
P016 | Project Q-16 (Stream 2) | Suresh | Sigmas | 2025-11-18 | 2026-04-25
P017 | Project R-17 (Stream 3) | Suresh | Kalpesh | 2025-11-03 | 2026-07-08
P018 | Project S-18 (Stream 1) | Abhi | Kalpesh | 2025-10-26 | 2026-06-29
P019 | Project T-19 (Stream 2) | Suresh | Rail | 2025-11-15 | 2026-04-10
P020 | Project U-20 (Stream 3) | Suresh | Kalpesh | 2026-01-09 | 2026-06-13

## DB_Resources
Resource_ID | Name | Role
R000 | Mike | Arch
R001 | Sarah | Dev
R002 | Jessica | QA
R003 | Tom | BA
R004 | Ravi | Lead
R005 | Siva | Arch
R006 | Wei | Dev
R007 | Lisa | QA

## DB_Allocations
Project_ID | Resource_ID | Allocation_Pct
P001 | R005 | 1
P001 | R000 | 1
P002 | R006 | 1
P002 | R001 | 1
P002 | R002 | 1
P003 | R000 | 1
P003 | R001 | 1
P003 | R003 | 0.5
P003 | R004 | 0.5
P004 | R002 | 1
P004 | R007 | 1
P004 | R005 | 0.5
P005 | R006 | 0.25
P005 | R003 | 0.25
P005 | R002 | 0.5
P006 | R001 | 1
P006 | R004 | 0.25
P006 | R005 | 1
P007 | R000 | 1
P007 | R003 | 0.5
P008 | R002 | 0.5
P008 | R007 | 0.25
P008 | R006 | 1
P009 | R005 | 0.5
P009 | R002 | 0.25
P009 | R006 | 0.5
P009 | R000 | 1
P010 | R007 | 0.5
P010 | R001 | 0.25
P010 | R002 | 0.25
P011 | R001 | 1
P011 | R000 | 0.5
P011 | R007 | 1
P012 | R003 | 0.5
P012 | R004 | 0.5
P012 | R001 | 1
P012 | R005 | 1
P013 | R006 | 1
P013 | R007 | 0.5
P014 | R007 | 0.25
P014 | R004 | 0.25
P015 | R006 | 0.5
P015 | R001 | 1
P015 | R000 | 0.25
P015 | R002 | 0.5
P016 | R007 | 0.25
P016 | R002 | 1
P016 | R003 | 0.25
P017 | R006 | 0.5
P017 | R003 | 1
P018 | R005 | 1
P018 | R000 | 0.5
P018 | R003 | 0.5
P019 | R003 | 0.25
P019 | R005 | 1
P019 | R002 | 1
P019 | R000 | 1
P020 | R007 | 0.5
P020 | R005 | 0.5
P020 | R002 | 0.25

## DB_Milestones
Project_ID | Milestone_Name | Due_Date | Status | Completion_Pct
P001 | Discovery | 2026-01-09 | Completed | 1
P001 | Design | 2026-01-29 | Completed | 1
P001 | Build | 2026-02-18 | In Progress | 0.5
P001 | UAT | 2026-03-10 | Pending | 0
P001 | Go-Live | 2026-03-30 | Pending | 0
P002 | Discovery | 2026-01-09 | Completed | 1
P002 | Design | 2026-01-29 | Completed | 1
P002 | Build | 2026-02-18 | In Progress | 0.5
P002 | UAT | 2026-03-10 | Pending | 0
P002 | Go-Live | 2026-03-30 | Pending | 0
P003 | Discovery | 2026-01-09 | Completed | 1
P003 | Design | 2026-01-29 | Completed | 1
P003 | Build | 2026-02-18 | In Progress | 0.5
P003 | UAT | 2026-03-10 | Pending | 0
P003 | Go-Live | 2026-03-30 | Pending | 0
P004 | Discovery | 2026-01-09 | Completed | 1
P004 | Design | 2026-01-29 | Completed | 1
P004 | Build | 2026-02-18 | In Progress | 0.5
P004 | UAT | 2026-03-10 | Pending | 0
P004 | Go-Live | 2026-03-30 | Pending | 0
P005 | Discovery | 2026-01-09 | Completed | 1
P005 | Design | 2026-01-29 | Completed | 1
P005 | Build | 2026-02-18 | In Progress | 0.5
P005 | UAT | 2026-03-10 | Pending | 0
P005 | Go-Live | 2026-03-30 | Pending | 0
P006 | Discovery | 2026-01-09 | Completed | 1
P006 | Design | 2026-01-29 | Completed | 1
P006 | Build | 2026-02-18 | In Progress | 0.5
P006 | UAT | 2026-03-10 | Pending | 0
P006 | Go-Live | 2026-03-30 | Pending | 0
P007 | Discovery | 2026-01-09 | Completed | 1
P007 | Design | 2026-01-29 | Completed | 1
P007 | Build | 2026-02-18 | In Progress | 0.5
P007 | UAT | 2026-03-10 | Pending | 0
P007 | Go-Live | 2026-03-30 | Pending | 0
P008 | Discovery | 2026-01-09 | Completed | 1
P008 | Design | 2026-01-29 | Completed | 1
P008 | Build | 2026-02-18 | In Progress | 0.5
P008 | UAT | 2026-03-10 | Pending | 0
P008 | Go-Live | 2026-03-30 | Pending | 0
P009 | Discovery | 2026-01-09 | Completed | 1
P009 | Design | 2026-01-29 | Completed | 1
P009 | Build | 2026-02-18 | In Progress | 0.5
P009 | UAT | 2026-03-10 | Pending | 0
P009 | Go-Live | 2026-03-30 | Pending | 0
P010 | Discovery | 2026-01-09 | Completed | 1
P010 | Design | 2026-01-29 | Completed | 1
P010 | Build | 2026-02-18 | In Progress | 0.5
P010 | UAT | 2026-03-10 | Pending | 0
P010 | Go-Live | 2026-03-30 | Pending | 0
P011 | Discovery | 2026-01-09 | Completed | 1
P011 | Design | 2026-01-29 | Completed | 1
P011 | Build | 2026-02-18 | In Progress | 0.5
P011 | UAT | 2026-03-10 | Pending | 0
P011 | Go-Live | 2026-03-30 | Pending | 0
P012 | Discovery | 2026-01-09 | Completed | 1
P012 | Design | 2026-01-29 | Completed | 1
P012 | Build | 2026-02-18 | In Progress | 0.5
P012 | UAT | 2026-03-10 | Pending | 0
P012 | Go-Live | 2026-03-30 | Pending | 0
P013 | Discovery | 2026-01-09 | Completed | 1
P013 | Design | 2026-01-29 | Completed | 1
P013 | Build | 2026-02-18 | In Progress | 0.5
P013 | UAT | 2026-03-10 | Pending | 0
P013 | Go-Live | 2026-03-30 | Pending | 0
P014 | Discovery | 2026-01-09 | Completed | 1
P014 | Design | 2026-01-29 | Completed | 1
P014 | Build | 2026-02-18 | In Progress | 0.5
P014 | UAT | 2026-03-10 | Pending | 0
P014 | Go-Live | 2026-03-30 | Pending | 0
P015 | Discovery | 2026-01-09 | Completed | 1
P015 | Design | 2026-01-29 | Completed | 1
P015 | Build | 2026-02-18 | In Progress | 0.5
P015 | UAT | 2026-03-10 | Pending | 0
P015 | Go-Live | 2026-03-30 | Pending | 0
P016 | Discovery | 2026-01-09 | Completed | 1
P016 | Design | 2026-01-29 | Completed | 1
P016 | Build | 2026-02-18 | In Progress | 0.5
P016 | UAT | 2026-03-10 | Pending | 0
P016 | Go-Live | 2026-03-30 | Pending | 0
P017 | Discovery | 2026-01-09 | Completed | 1
P017 | Design | 2026-01-29 | Completed | 1
P017 | Build | 2026-02-18 | In Progress | 0.5
P017 | UAT | 2026-03-10 | Pending | 0
P017 | Go-Live | 2026-03-30 | Pending | 0
P018 | Discovery | 2026-01-09 | Completed | 1
P018 | Design | 2026-01-29 | Completed | 1
P018 | Build | 2026-02-18 | In Progress | 0.5
P018 | UAT | 2026-03-10 | Pending | 0
P018 | Go-Live | 2026-03-30 | Pending | 0
P019 | Discovery | 2026-01-09 | Completed | 1
P019 | Design | 2026-01-29 | Completed | 1
P019 | Build | 2026-02-18 | In Progress | 0.5
P019 | UAT | 2026-03-10 | Pending | 0
P019 | Go-Live | 2026-03-30 | Pending | 0
P020 | Discovery | 2026-01-09 | Completed | 1
P020 | Design | 2026-01-29 | Completed | 1
P020 | Build | 2026-02-18 | In Progress | 0.5
P020 | UAT | 2026-03-10 | Pending | 0
P020 | Go-Live | 2026-03-30 | Pending | 0

## DB_Updates
Project_ID | Week_No | Overall_RAG | Goal_This_Week | Key_Achievements | Top_Risk | Weekly_Status_Narrative
P001 | Wk 04 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | None | Progress is steady. On track.
P002 | Wk 04 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | None | Progress is steady. On track.
P003 | Wk 04 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | None | Progress is steady. On track.
P004 | Wk 04 | Green | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | None | Progress is steady. On track.
P005 | Wk 04 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | Data latency issues in QA env | Progress is steady. Critical blocker on API.
P006 | Wk 04 | Green | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | None | Progress is steady. On track.
P007 | Wk 04 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | None | Progress is steady. On track.
P008 | Wk 04 | Green | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | None | Progress is steady. On track.
P009 | Wk 04 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | Data latency issues in QA env | Progress is steady. Critical blocker on API.
P010 | Wk 04 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | Data latency issues in QA env | Progress is steady. Critical blocker on API.
P011 | Wk 04 | Green | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | None | Progress is steady. On track.
P012 | Wk 04 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | Data latency issues in QA env | Progress is steady. Critical blocker on API.
P013 | Wk 04 | Green | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | None | Progress is steady. On track.
P014 | Wk 04 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | Data latency issues in QA env | Progress is steady. Critical blocker on API.
P015 | Wk 04 | Green | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | None | Progress is steady. On track.
P016 | Wk 04 | Green | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | None | Progress is steady. On track.
P017 | Wk 04 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | None | Progress is steady. On track.
P018 | Wk 04 | Red | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | Data latency issues in QA env | Progress is steady. Critical blocker on API.
P019 | Wk 04 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | None | Progress is steady. On track.
P020 | Wk 04 | Amber | Finalize UAT Sign-off and prepare deployment scripts. | Completed Module B coding. All Priority 1 bugs closed. | None | Progress is steady. On track.

## DB_SLA
Project_ID | Metric | Status
P001 | Defect Turnaround | Breached
P001 | Uptime | Met
P002 | Defect Turnaround | Breached
P002 | Uptime | Met
P003 | Defect Turnaround | Met
P003 | Uptime | Met
P004 | Defect Turnaround | Breached
P004 | Uptime | Met
P005 | Defect Turnaround | Met
P005 | Uptime | Met
P006 | Defect Turnaround | Met
P006 | Uptime | Met
P007 | Defect Turnaround | Met
P007 | Uptime | Met
P008 | Defect Turnaround | Met
P008 | Uptime | Met
P009 | Defect Turnaround | Met
P009 | Uptime | Met
P010 | Defect Turnaround | Met
P010 | Uptime | Met
P011 | Defect Turnaround | Met
P011 | Uptime | Met
P012 | Defect Turnaround | Met
P012 | Uptime | Met
P013 | Defect Turnaround | Met
P013 | Uptime | Met
P014 | Defect Turnaround | Breached
P014 | Uptime | Met
P015 | Defect Turnaround | Met
P015 | Uptime | Met
P016 | Defect Turnaround | Breached
P016 | Uptime | Met
P017 | Defect Turnaround | Breached
P017 | Uptime | Met
P018 | Defect Turnaround | Breached
P018 | Uptime | Met
P019 | Defect Turnaround | Met
P019 | Uptime | Met
P020 | Defect Turnaround | Met
P020 | Uptime | Met