## >> DEMAND_PLAN <<
Portfolio | Team | Skill Required | Level | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27 | Jun-27 | Jul-27 | Aug-27 | Sep-27 | Oct-27 | Nov-27 | Dec-27
Legacy Modernization | Squad Beta | SAP ABAP | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Digital Transformation | Squad Beta | Cloud/DevOps | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Legacy Modernization | Squad Alpha | SAP ABAP | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Data & AI | Squad Beta | SAP ABAP | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Digital Transformation | Squad Alpha | Java Fullstack | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2
Cloud Infra | Squad Beta | Java Fullstack | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
Cloud Infra | Core Ops | Python/AI | Standard | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data & AI | Squad Gamma | Data Engineering | Senior | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Digital Transformation | Squad Beta | Data Engineering | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
Digital Transformation | Squad Beta | Python/AI | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Digital Transformation | Squad Alpha | SAP ABAP | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cloud Infra | Squad Alpha | Python/AI | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Cloud Infra | Squad Gamma | Cloud/DevOps | Senior | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data & AI | Core Ops | Python/AI | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cloud Infra | Squad Alpha | SAP ABAP | Senior | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data & AI | Squad Alpha | Data Engineering | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
Cloud Infra | Squad Alpha | SAP ABAP | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
Data & AI | Squad Beta | Java Fullstack | Senior | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cloud Infra | Core Ops | Cloud/DevOps | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
Cloud Infra | Squad Beta | Java Fullstack | Senior | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
Digital Transformation | Squad Beta | Python/AI | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
Data & AI | Squad Beta | Java Fullstack | Standard | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Digital Transformation | Squad Gamma | SAP ABAP | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1
Cloud Infra | Squad Gamma | SAP ABAP | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Data & AI | Squad Gamma | Python/AI | Standard | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Digital Transformation | Squad Beta | SAP ABAP | Standard | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Digital Transformation | Squad Gamma | Java Fullstack | Senior | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0

## >> DASHBOARD <<
Project | Portfolio | Team | Status | Roadmap | Resources | Narrative | Tasks
Project U-20 | Cloud Infra | Core Ops | Amber | ✅ Discovery ✅ Build | • John (Data Engineering) • Tom (Data Engineering) | GOAL: Finalize UAT RISK: Resource constraints | 1. API Spec 2. UAT Plan
Project H-07 | Cloud Infra | Squad Alpha | Green | ✅ Discovery ✅ Build | • Mike (Data Engineering) • Sarah (Java Fullstack) | GOAL: Finalize UAT RISK: None | 1. API Spec 2. UAT Plan
Project T-19 | Cloud Infra | Squad Alpha | Green | ✅ Discovery ✅ Build | • Siva (Data Engineering) • Mike (Data Engineering) • Jessica (Data Engineering) | GOAL: Finalize UAT RISK: None | 1. API Spec 2. UAT Plan
Project M-12 | Cloud Infra | Squad Beta | Amber | ✅ Discovery ✅ Build | • John (Data Engineering) • Priya (Cloud/DevOps) • Ravi (SAP ABAP) | GOAL: Finalize UAT RISK: Resource constraints | 1. API Spec 2. UAT Plan
Project V-21 | Cloud Infra | Squad Beta | Red | ✅ Discovery ✅ Build | • John (Data Engineering) • Wei (Python/AI) | GOAL: Finalize UAT RISK: Resource constraints | 1. API Spec 2. UAT Plan
Project O-14 | Cloud Infra | Squad Gamma | Amber | ✅ Discovery ✅ Build | • John (Data Engineering) • Ravi (SAP ABAP) • Tom (Data Engineering) | GOAL: Finalize UAT RISK: Resource constraints | 1. API Spec 2. UAT Plan
Project Z-25 | Cloud Infra | Squad Gamma | Red | ✅ Discovery ✅ Build | • Wei (Python/AI) • Sarah (Java Fullstack) | GOAL: Finalize UAT RISK: Resource constraints | 1. API Spec 2. UAT Plan
Project F-05 | Data & AI | Core Ops | Amber | ✅ Discovery ✅ Build | • Siva (Data Engineering) • Lisa (Data Engineering) | GOAL: Finalize UAT RISK: Resource constraints | 1. API Spec 2. UAT Plan
Project Q-16 | Data & AI | Squad Alpha | Green | ✅ Discovery ✅ Build | • Lisa (Data Engineering) • Wei (Python/AI) • Siva (Data Engineering) | GOAL: Finalize UAT RISK: None | 1. API Spec 2. UAT Plan
Project J-09 | Data & AI | Squad Beta | Green | ✅ Discovery ✅ Build | • Wei (Python/AI) • John (Data Engineering) • Siva (Data Engineering) | GOAL: Finalize UAT RISK: None | 1. API Spec 2. UAT Plan
Project D-03 | Data & AI | Squad Gamma | Red | ✅ Discovery ✅ Build | • Ravi (SAP ABAP) • Sarah (Java Fullstack) | GOAL: Finalize UAT RISK: Resource constraints | 1. API Spec 2. UAT Plan
Project N-13 | Digital Transformation | Core Ops | Green | ✅ Discovery ✅ Build | • Siva (Data Engineering) • Sarah (Java Fullstack) | GOAL: Finalize UAT RISK: None | 1. API Spec 2. UAT Plan
Project B-01 | Digital Transformation | Squad Alpha | Green | ✅ Discovery ✅ Build | • Lisa (Data Engineering) • Ravi (SAP ABAP) • Siva (Data Engineering) | GOAL: Finalize UAT RISK: None | 1. API Spec 2. UAT Plan
Project K-10 | Digital Transformation | Squad Alpha | Green | ✅ Discovery ✅ Build | • Priya (Cloud/DevOps) • Tom (Data Engineering) • Mike (Data Engineering) | GOAL: Finalize UAT RISK: None | 1. API Spec 2. UAT Plan
Project R-17 | Digital Transformation | Squad Alpha | Red | ✅ Discovery ✅ Build | • Lisa (Data Engineering) • Priya (Cloud/DevOps) | GOAL: Finalize UAT RISK: Resource constraints | 1. API Spec 2. UAT Plan
Project Y-24 | Digital Transformation | Squad Alpha | Amber | ✅ Discovery ✅ Build | • Jessica (Data Engineering) • Tom (Data Engineering) • Siva (Data Engineering) | GOAL: Finalize UAT RISK: Resource constraints | 1. API Spec 2. UAT Plan
Project C-02 | Digital Transformation | Squad Beta | Red | ✅ Discovery ✅ Build | • Ravi (SAP ABAP) • Wei (Python/AI) • Priya (Cloud/DevOps) | GOAL: Finalize UAT RISK: Resource constraints | 1. API Spec 2. UAT Plan
Project L-11 | Digital Transformation | Squad Beta | Green | ✅ Discovery ✅ Build | • Tom (Data Engineering) • Mike (Data Engineering) • Wei (Python/AI) | GOAL: Finalize UAT RISK: None | 1. API Spec 2. UAT Plan
Project E-04 | Digital Transformation | Squad Gamma | Red | ✅ Discovery ✅ Build | • Siva (Data Engineering) • Lisa (Data Engineering) • John (Data Engineering) | GOAL: Finalize UAT RISK: Resource constraints | 1. API Spec 2. UAT Plan
Project W-22 | Digital Transformation | Squad Gamma | Red | ✅ Discovery ✅ Build | • Wei (Python/AI) • Lisa (Data Engineering) | GOAL: Finalize UAT RISK: Resource constraints | 1. API Spec 2. UAT Plan
Project G-06 | Legacy Modernization | Core Ops | Green | ✅ Discovery ✅ Build | • Ravi (SAP ABAP) • Sarah (Java Fullstack) | GOAL: Finalize UAT RISK: None | 1. API Spec 2. UAT Plan
Project P-15 | Legacy Modernization | Core Ops | Green | ✅ Discovery ✅ Build | • Lisa (Data Engineering) • Jessica (Data Engineering) • Siva (Data Engineering) | GOAL: Finalize UAT RISK: None | 1. API Spec 2. UAT Plan
Project X-23 | Legacy Modernization | Core Ops | Red | ✅ Discovery ✅ Build | • John (Data Engineering) • Siva (Data Engineering) | GOAL: Finalize UAT RISK: Resource constraints | 1. API Spec 2. UAT Plan
Project S-18 | Legacy Modernization | Squad Beta | Green | ✅ Discovery ✅ Build | • Siva (Data Engineering) • Jessica (Data Engineering) | GOAL: Finalize UAT RISK: None | 1. API Spec 2. UAT Plan
Project I-08 | Legacy Modernization | Squad Gamma | Amber | ✅ Discovery ✅ Build | • Lisa (Data Engineering) • Ravi (SAP ABAP) • Jessica (Data Engineering) | GOAL: Finalize UAT RISK: Resource constraints | 1. API Spec 2. UAT Plan

## DB_Pipeline
Pipeline_ID | Project_ID | Portfolio | Team | Skill_ID | Skill_Level_Needed | Start_Date | End_Date | Solution_Architect | Product_Owner | LTIM_Lead
PIPE-001 | NEW-PROJ-1 | Legacy Modernization | Squad Beta | S03 | Senior | 2027-11-01 | 2028-06-01 | TBD | TBD | TBD
PIPE-002 | NEW-PROJ-2 | Digital Transformation | Squad Beta | S05 | Senior | 2026-08-01 | 2027-01-01 | TBD | TBD | TBD
PIPE-003 | NEW-PROJ-3 | Legacy Modernization | Squad Alpha | S03 | Standard | 2027-09-01 | 2028-05-01 | TBD | TBD | TBD
PIPE-004 | NEW-PROJ-4 | Data & AI | Squad Beta | S03 | Senior | 2027-12-01 | 2028-08-01 | TBD | TBD | TBD
PIPE-005 | NEW-PROJ-5 | Digital Transformation | Squad Alpha | S01 | Standard | 2027-11-01 | 2028-05-01 | TBD | TBD | TBD
PIPE-006 | NEW-PROJ-6 | Cloud Infra | Squad Beta | S01 | Standard | 2027-10-01 | 2028-04-01 | TBD | TBD | TBD
PIPE-007 | NEW-PROJ-7 | Cloud Infra | Core Ops | S02 | Standard | 2026-06-01 | 2026-11-01 | TBD | TBD | TBD
PIPE-008 | NEW-PROJ-8 | Data & AI | Squad Gamma | S04 | Senior | 2026-01-01 | 2026-04-01 | TBD | TBD | TBD
PIPE-009 | NEW-PROJ-9 | Digital Transformation | Squad Beta | S04 | Senior | 2027-07-01 | 2027-12-01 | TBD | TBD | TBD
PIPE-010 | NEW-PROJ-10 | Digital Transformation | Squad Beta | S02 | Senior | 2027-01-01 | 2027-10-01 | TBD | TBD | TBD
PIPE-011 | NEW-PROJ-11 | Digital Transformation | Squad Alpha | S03 | Standard | 2026-10-01 | 2027-04-01 | TBD | TBD | TBD
PIPE-012 | NEW-PROJ-12 | Cloud Infra | Squad Alpha | S02 | Standard | 2027-11-01 | 2028-03-01 | TBD | TBD | TBD
PIPE-013 | NEW-PROJ-13 | Cloud Infra | Squad Gamma | S05 | Senior | 2026-03-01 | 2026-09-01 | TBD | TBD | TBD
PIPE-014 | NEW-PROJ-14 | Data & AI | Core Ops | S02 | Senior | 2026-09-01 | 2027-01-01 | TBD | TBD | TBD
PIPE-015 | NEW-PROJ-15 | Cloud Infra | Squad Alpha | S03 | Senior | 2026-05-01 | 2026-10-01 | TBD | TBD | TBD
PIPE-016 | NEW-PROJ-16 | Data & AI | Squad Alpha | S04 | Standard | 2027-08-01 | 2027-12-01 | TBD | TBD | TBD
PIPE-017 | NEW-PROJ-17 | Cloud Infra | Squad Alpha | S03 | Standard | 2027-12-01 | 2028-06-01 | TBD | TBD | TBD
PIPE-018 | NEW-PROJ-18 | Data & AI | Squad Beta | S01 | Senior | 2026-01-01 | 2026-07-01 | TBD | TBD | TBD
PIPE-019 | NEW-PROJ-19 | Cloud Infra | Core Ops | S05 | Standard | 2027-10-01 | 2028-07-01 | TBD | TBD | TBD
PIPE-020 | NEW-PROJ-20 | Cloud Infra | Squad Beta | S01 | Senior | 2026-03-01 | 2026-09-01 | TBD | TBD | TBD
PIPE-021 | NEW-PROJ-21 | Digital Transformation | Squad Alpha | S01 | Standard | 2027-04-01 | 2027-12-01 | TBD | TBD | TBD
PIPE-022 | NEW-PROJ-22 | Digital Transformation | Squad Beta | S02 | Standard | 2026-10-01 | 2027-07-01 | TBD | TBD | TBD
PIPE-023 | NEW-PROJ-23 | Cloud Infra | Squad Beta | S01 | Senior | 2027-11-01 | 2028-02-01 | TBD | TBD | TBD
PIPE-024 | NEW-PROJ-24 | Data & AI | Squad Beta | S01 | Standard | 2026-05-01 | 2027-02-01 | TBD | TBD | TBD
PIPE-025 | NEW-PROJ-25 | Digital Transformation | Squad Gamma | S03 | Senior | 2027-07-01 | 2028-04-01 | TBD | TBD | TBD
PIPE-026 | NEW-PROJ-26 | Cloud Infra | Squad Gamma | S03 | Senior | 2027-02-01 | 2027-05-01 | TBD | TBD | TBD
PIPE-027 | NEW-PROJ-27 | Data & AI | Squad Gamma | S02 | Standard | 2026-03-01 | 2026-07-01 | TBD | TBD | TBD
PIPE-028 | NEW-PROJ-28 | Data & AI | Squad Gamma | S02 | Standard | 2026-06-01 | 2026-11-01 | TBD | TBD | TBD
PIPE-029 | NEW-PROJ-29 | Digital Transformation | Squad Beta | S03 | Standard | 2026-08-01 | 2026-12-01 | TBD | TBD | TBD
PIPE-030 | NEW-PROJ-30 | Digital Transformation | Squad Gamma | S01 | Senior | 2027-08-01 | 2027-11-01 | TBD | TBD | TBD

## DB_Skills
Skill_ID | Skill_Name | Levels
S01 | Java Fullstack | L1, L2, L3
S02 | Python/AI | L1, L2, L3
S03 | SAP ABAP | L1, L2, L3
S04 | Data Engineering | L1, L2, L3
S05 | Cloud/DevOps | L1, L2, L3

## DB_Resources
Resource_ID | Full_Name | Skill_ID | Skill_Level | Years_Exp | Manager
R000 | Mike | S04 | Standard | 3 | Director A
R001 | Sarah | S01 | Junior | 3 | Director B
R002 | Jessica | S04 | Standard | 2 | Director B
R003 | Tom | S04 | Senior | 12 | Director B
R004 | Ravi | S03 | Senior | 13 | Director B
R005 | Siva | S04 | Senior | 4 | Director A
R006 | Wei | S02 | Senior | 11 | Director B
R007 | Lisa | S04 | Senior | 10 | Director B
R008 | John | S04 | Senior | 11 | Director A
R009 | Priya | S05 | Junior | 7 | Director A

## DB_Projects
Project_ID | Project_Name | Portfolio | Team | Lead | PM | Kickoff | End_Date
P001 | Project B-01 | Digital Transformation | Squad Alpha | Brandi | Rail | 2026-01-02 | 2026-07-01
P002 | Project C-02 | Digital Transformation | Squad Beta | Brandi | Kalpesh | 2026-01-02 | 2026-07-01
P003 | Project D-03 | Data & AI | Squad Gamma | Brandi | Rail | 2026-01-02 | 2026-07-01
P004 | Project E-04 | Digital Transformation | Squad Gamma | Suresh | Rail | 2026-01-02 | 2026-07-01
P005 | Project F-05 | Data & AI | Core Ops | Abhi | Kalpesh | 2026-01-02 | 2026-07-01
P006 | Project G-06 | Legacy Modernization | Core Ops | Brandi | Rail | 2026-01-02 | 2026-07-01
P007 | Project H-07 | Cloud Infra | Squad Alpha | Suresh | Kalpesh | 2026-01-02 | 2026-07-01
P008 | Project I-08 | Legacy Modernization | Squad Gamma | Brandi | Rail | 2026-01-02 | 2026-07-01
P009 | Project J-09 | Data & AI | Squad Beta | Brandi | Kalpesh | 2026-01-02 | 2026-07-01
P010 | Project K-10 | Digital Transformation | Squad Alpha | Brandi | Kalpesh | 2026-01-02 | 2026-07-01
P011 | Project L-11 | Digital Transformation | Squad Beta | Abhi | Rail | 2026-01-02 | 2026-07-01
P012 | Project M-12 | Cloud Infra | Squad Beta | Stanley | Rail | 2026-01-02 | 2026-07-01
P013 | Project N-13 | Digital Transformation | Core Ops | Abhi | Rail | 2026-01-02 | 2026-07-01
P014 | Project O-14 | Cloud Infra | Squad Gamma | Stanley | Kalpesh | 2026-01-02 | 2026-07-01
P015 | Project P-15 | Legacy Modernization | Core Ops | Abhi | Kalpesh | 2026-01-02 | 2026-07-01
P016 | Project Q-16 | Data & AI | Squad Alpha | Abhi | Rail | 2026-01-02 | 2026-07-01
P017 | Project R-17 | Digital Transformation | Squad Alpha | Stanley | Rail | 2026-01-02 | 2026-07-01
P018 | Project S-18 | Legacy Modernization | Squad Beta | Abhi | Rail | 2026-01-02 | 2026-07-01
P019 | Project T-19 | Cloud Infra | Squad Alpha | Stanley | Rail | 2026-01-02 | 2026-07-01
P020 | Project U-20 | Cloud Infra | Core Ops | Stanley | Kalpesh | 2026-01-02 | 2026-07-01
P021 | Project V-21 | Cloud Infra | Squad Beta | Abhi | Rail | 2026-01-02 | 2026-07-01
P022 | Project W-22 | Digital Transformation | Squad Gamma | Suresh | Kalpesh | 2026-01-02 | 2026-07-01
P023 | Project X-23 | Legacy Modernization | Core Ops | Suresh | Rail | 2026-01-02 | 2026-07-01
P024 | Project Y-24 | Digital Transformation | Squad Alpha | Suresh | Rail | 2026-01-02 | 2026-07-01
P025 | Project Z-25 | Cloud Infra | Squad Gamma | Suresh | Kalpesh | 2026-01-02 | 2026-07-01

## DB_Allocations
Project_ID | Resource_ID | Allocation_% | Start_Date | End_Date
P001 | R007 | 0.5 | 2026-01-22 | 2026-04-22
P001 | R004 | 1 | 2026-01-22 | 2026-04-22
P001 | R005 | 0.5 | 2026-01-22 | 2026-04-22
P002 | R004 | 0.5 | 2026-01-22 | 2026-04-22
P002 | R006 | 0.5 | 2026-01-22 | 2026-04-22
P002 | R009 | 0.5 | 2026-01-22 | 2026-04-22
P003 | R004 | 1 | 2026-01-22 | 2026-04-22
P003 | R001 | 1 | 2026-01-22 | 2026-04-22
P004 | R005 | 1 | 2026-01-22 | 2026-04-22
P004 | R007 | 1 | 2026-01-22 | 2026-04-22
P004 | R008 | 1 | 2026-01-22 | 2026-04-22
P005 | R005 | 0.5 | 2026-01-22 | 2026-04-22
P005 | R007 | 0.5 | 2026-01-22 | 2026-04-22
P006 | R004 | 0.5 | 2026-01-22 | 2026-04-22
P006 | R001 | 1 | 2026-01-22 | 2026-04-22
P007 | R000 | 1 | 2026-01-22 | 2026-04-22
P007 | R001 | 0.5 | 2026-01-22 | 2026-04-22
P008 | R007 | 1 | 2026-01-22 | 2026-04-22
P008 | R004 | 0.5 | 2026-01-22 | 2026-04-22
P008 | R002 | 1 | 2026-01-22 | 2026-04-22
P009 | R006 | 0.5 | 2026-01-22 | 2026-04-22
P009 | R008 | 0.5 | 2026-01-22 | 2026-04-22
P009 | R005 | 1 | 2026-01-22 | 2026-04-22
P010 | R009 | 1 | 2026-01-22 | 2026-04-22
P010 | R003 | 1 | 2026-01-22 | 2026-04-22
P010 | R000 | 1 | 2026-01-22 | 2026-04-22
P011 | R003 | 1 | 2026-01-22 | 2026-04-22
P011 | R000 | 1 | 2026-01-22 | 2026-04-22
P011 | R006 | 1 | 2026-01-22 | 2026-04-22
P012 | R008 | 0.5 | 2026-01-22 | 2026-04-22
P012 | R009 | 1 | 2026-01-22 | 2026-04-22
P012 | R004 | 0.5 | 2026-01-22 | 2026-04-22
P013 | R005 | 0.5 | 2026-01-22 | 2026-04-22
P013 | R001 | 1 | 2026-01-22 | 2026-04-22
P014 | R008 | 1 | 2026-01-22 | 2026-04-22
P014 | R004 | 0.5 | 2026-01-22 | 2026-04-22
P014 | R003 | 0.5 | 2026-01-22 | 2026-04-22
P015 | R007 | 0.5 | 2026-01-22 | 2026-04-22
P015 | R002 | 0.5 | 2026-01-22 | 2026-04-22
P015 | R005 | 0.5 | 2026-01-22 | 2026-04-22
P016 | R007 | 0.5 | 2026-01-22 | 2026-04-22
P016 | R006 | 0.5 | 2026-01-22 | 2026-04-22
P016 | R005 | 1 | 2026-01-22 | 2026-04-22
P017 | R007 | 1 | 2026-01-22 | 2026-04-22
P017 | R009 | 0.5 | 2026-01-22 | 2026-04-22
P018 | R005 | 0.5 | 2026-01-22 | 2026-04-22
P018 | R002 | 0.5 | 2026-01-22 | 2026-04-22
P019 | R005 | 0.5 | 2026-01-22 | 2026-04-22
P019 | R000 | 1 | 2026-01-22 | 2026-04-22
P019 | R002 | 0.5 | 2026-01-22 | 2026-04-22
P020 | R008 | 1 | 2026-01-22 | 2026-04-22
P020 | R003 | 0.5 | 2026-01-22 | 2026-04-22
P021 | R008 | 1 | 2026-01-22 | 2026-04-22
P021 | R006 | 0.5 | 2026-01-22 | 2026-04-22
P022 | R006 | 0.5 | 2026-01-22 | 2026-04-22
P022 | R007 | 0.5 | 2026-01-22 | 2026-04-22
P023 | R008 | 1 | 2026-01-22 | 2026-04-22
P023 | R005 | 1 | 2026-01-22 | 2026-04-22
P024 | R002 | 0.5 | 2026-01-22 | 2026-04-22
P024 | R003 | 1 | 2026-01-22 | 2026-04-22
P024 | R005 | 1 | 2026-01-22 | 2026-04-22
P025 | R006 | 0.5 | 2026-01-22 | 2026-04-22
P025 | R001 | 1 | 2026-01-22 | 2026-04-22

## DB_Updates
Project_ID | Week | RAG | Goal | Narrative | Tasks | Risks
P001 | Wk 05 | Green | Finalize UAT | On track | 1. API Spec 2. UAT Plan | None
P002 | Wk 05 | Red | Finalize UAT | Delays due to API | 1. API Spec 2. UAT Plan | Resource constraints
P003 | Wk 05 | Red | Finalize UAT | Delays due to API | 1. API Spec 2. UAT Plan | Resource constraints
P004 | Wk 05 | Red | Finalize UAT | Delays due to API | 1. API Spec 2. UAT Plan | Resource constraints
P005 | Wk 05 | Amber | Finalize UAT | On track | 1. API Spec 2. UAT Plan | Resource constraints
P006 | Wk 05 | Green | Finalize UAT | On track | 1. API Spec 2. UAT Plan | None
P007 | Wk 05 | Green | Finalize UAT | On track | 1. API Spec 2. UAT Plan | None
P008 | Wk 05 | Amber | Finalize UAT | On track | 1. API Spec 2. UAT Plan | Resource constraints
P009 | Wk 05 | Green | Finalize UAT | On track | 1. API Spec 2. UAT Plan | None
P010 | Wk 05 | Green | Finalize UAT | On track | 1. API Spec 2. UAT Plan | None
P011 | Wk 05 | Green | Finalize UAT | On track | 1. API Spec 2. UAT Plan | None
P012 | Wk 05 | Amber | Finalize UAT | On track | 1. API Spec 2. UAT Plan | Resource constraints
P013 | Wk 05 | Green | Finalize UAT | On track | 1. API Spec 2. UAT Plan | None
P014 | Wk 05 | Amber | Finalize UAT | On track | 1. API Spec 2. UAT Plan | Resource constraints
P015 | Wk 05 | Green | Finalize UAT | On track | 1. API Spec 2. UAT Plan | None
P016 | Wk 05 | Green | Finalize UAT | On track | 1. API Spec 2. UAT Plan | None
P017 | Wk 05 | Red | Finalize UAT | Delays due to API | 1. API Spec 2. UAT Plan | Resource constraints
P018 | Wk 05 | Green | Finalize UAT | On track | 1. API Spec 2. UAT Plan | None
P019 | Wk 05 | Green | Finalize UAT | On track | 1. API Spec 2. UAT Plan | None
P020 | Wk 05 | Amber | Finalize UAT | On track | 1. API Spec 2. UAT Plan | Resource constraints
P021 | Wk 05 | Red | Finalize UAT | Delays due to API | 1. API Spec 2. UAT Plan | Resource constraints
P022 | Wk 05 | Red | Finalize UAT | Delays due to API | 1. API Spec 2. UAT Plan | Resource constraints
P023 | Wk 05 | Red | Finalize UAT | Delays due to API | 1. API Spec 2. UAT Plan | Resource constraints
P024 | Wk 05 | Amber | Finalize UAT | On track | 1. API Spec 2. UAT Plan | Resource constraints
P025 | Wk 05 | Red | Finalize UAT | Delays due to API | 1. API Spec 2. UAT Plan | Resource constraints

## DB_Milestones
Project_ID | Milestone | Date | Status
P001 | Discovery | 2026-02-15 | Done
P001 | Build | 2026-04-10 | In Progress
P002 | Discovery | 2026-02-15 | Done
P002 | Build | 2026-04-10 | In Progress
P003 | Discovery | 2026-02-15 | Done
P003 | Build | 2026-04-10 | In Progress
P004 | Discovery | 2026-02-15 | Done
P004 | Build | 2026-04-10 | In Progress
P005 | Discovery | 2026-02-15 | Done
P005 | Build | 2026-04-10 | In Progress
P006 | Discovery | 2026-02-15 | Done
P006 | Build | 2026-04-10 | In Progress
P007 | Discovery | 2026-02-15 | Done
P007 | Build | 2026-04-10 | In Progress
P008 | Discovery | 2026-02-15 | Done
P008 | Build | 2026-04-10 | In Progress
P009 | Discovery | 2026-02-15 | Done
P009 | Build | 2026-04-10 | In Progress
P010 | Discovery | 2026-02-15 | Done
P010 | Build | 2026-04-10 | In Progress
P011 | Discovery | 2026-02-15 | Done
P011 | Build | 2026-04-10 | In Progress
P012 | Discovery | 2026-02-15 | Done
P012 | Build | 2026-04-10 | In Progress
P013 | Discovery | 2026-02-15 | Done
P013 | Build | 2026-04-10 | In Progress
P014 | Discovery | 2026-02-15 | Done
P014 | Build | 2026-04-10 | In Progress
P015 | Discovery | 2026-02-15 | Done
P015 | Build | 2026-04-10 | In Progress
P016 | Discovery | 2026-02-15 | Done
P016 | Build | 2026-04-10 | In Progress
P017 | Discovery | 2026-02-15 | Done
P017 | Build | 2026-04-10 | In Progress
P018 | Discovery | 2026-02-15 | Done
P018 | Build | 2026-04-10 | In Progress
P019 | Discovery | 2026-02-15 | Done
P019 | Build | 2026-04-10 | In Progress
P020 | Discovery | 2026-02-15 | Done
P020 | Build | 2026-04-10 | In Progress
P021 | Discovery | 2026-02-15 | Done
P021 | Build | 2026-04-10 | In Progress
P022 | Discovery | 2026-02-15 | Done
P022 | Build | 2026-04-10 | In Progress
P023 | Discovery | 2026-02-15 | Done
P023 | Build | 2026-04-10 | In Progress
P024 | Discovery | 2026-02-15 | Done
P024 | Build | 2026-04-10 | In Progress
P025 | Discovery | 2026-02-15 | Done
P025 | Build | 2026-04-10 | In Progress

## DB_SLA
Project_ID | Metric | Status
P001 | Defect SLA | Met
P002 | Defect SLA | Met
P003 | Defect SLA | Met
P004 | Defect SLA | Met
P005 | Defect SLA | Met
P006 | Defect SLA | Met
P007 | Defect SLA | Met
P008 | Defect SLA | Met
P009 | Defect SLA | Met
P010 | Defect SLA | Met
P011 | Defect SLA | Met
P012 | Defect SLA | Met
P013 | Defect SLA | Met
P014 | Defect SLA | Met
P015 | Defect SLA | Met
P016 | Defect SLA | Met
P017 | Defect SLA | Met
P018 | Defect SLA | Met
P019 | Defect SLA | Met
P020 | Defect SLA | Met
P021 | Defect SLA | Met
P022 | Defect SLA | Met
P023 | Defect SLA | Met
P024 | Defect SLA | Met
P025 | Defect SLA | Met